Table of Contents:

SECTION- I:  PROCUREMENT PLANNING	3

1.	District Development Plan	3

2.	Annual Procurement Plan	3

3.	Cost Estimate	3

4.	Implementation	4

4.1	Implementation of Short Span Trail Bridge (SSTB) / Community Bridges	4

4.2	Nomination of NGO	4

4.3	Procurement of “Foreign Materials”	4

4.4	Transportation (Portering), Construction and Bridge Erection	4

SECTION - II:  PROCUREMENT METHODS	5

5.	Selection of Procurement Method	5

5.1	Community Based Procurement Method	5

5.2	Open Bid Method	5

5.2.1	Fabrication Package [FP]	5

5.2.2	Engineering Package [EP]	5

SECTION - III:  BIDDING PROCEDURES	6

6.	Bidding Procedures	6

6.1	Tender Packages	6

6.2	Contract Period	6

6.3	Preparation of Standard Bidding Document (SBD)	6

6.3.1	Instruction to Bidders (ITB)	6

6.3.2	Bidding Data Sheet	7

6.3.3	General Conditions of Contract (GCC)	7

6.3.4	Special Conditions of Contract (SCC)	7

6.4	Invitation For Bid (IFB)	7

6.5	Distribution of Standard Bidding Documents	8

6.6	Pre-bid Conference	8

6.7	Preparation and Submission of Bid	9

7.	Requirements Applicable to Bid Securities	9

8.	Bid-validity Period	10

9.	Bid Opening	10

SECTION - IV:  BID EVALUATION	10

10.	Bid Evaluation	10

10.1	Reception and Security of Bids	11

10.2	Rejection of Late Bids	11

10.3	Bid Evaluation Committee	11

10.4	Bid Evaluation Procedure	11

10.5	Preliminary Examination for Completeness of Bids	12

10.5.1	Determination of Responsiveness of Bids	12

10.5.2	Clarification of Bids	12

10.5.3	Correction of Arithmetical and Computational Errors	13

10.5.4	Detailed Technical Evaluation of Responsive Bids (Technical Proposal)	13

10.5.5	Evaluation of Financial Proposal	15

10.5.6	Determination of Lowest Evaluated Responsive Bid	15

10.5.7	Confidentiality of Bid Evaluation	15

10.5.8	Rejection of Bids and Re-bidding	15

SECTION - V:  Contract Management	15

11.	Notification of Award	15

12.	Performance Security	15

13.	Contract Award	16

13.1	Contract Limit	16

13.2	Witness	16

14.	The Services	16

15.	Commencement Date	16

16.	Orientation	16

17.	Execution of Work	16

18.	Technical Support, Quality Monitoring, Inspection and Acceptance	17

18.1	Inspection and Quality Control of Steel Parts	17

18.2	Technical Support and Quality Control of Construction & Bridge Erection Works	17

18.2.1  Work Completion Report (WCR)	17

18.2.2  Work Completion Certificate (WCC)	17

19.	Payment Procedures	18

19.1	Advance	18

19.2	Payment	18

19.3	Place of Payment	18

20.	Notice of Delay	18

21.	Time Extension	18

22.	Penalties for Delay	18

23.	Settlement of Disputes	18

24.	Third Party Technical Audit	18

SECTION - VI:  Miscellaneous	19

25.	Internal DDC Contract Management Procedure Table	19

26.	Record Keeping Requirements	19

# SECTION- I:  PROCUREMENT PLANNING

## 1.	District Development Plan

District Development Plan for the procurement of Civil Works, Consulting Services and Goods in the district should be prepared and approved as per Local Self Governance Act and its Regulations.

(1.1)   	for all Trail Bridges that have to be constructed, a procurement plan shall be prepared, and such plan should outline following aspects:

- Number of trail bridges (New construction and maintenance), that are to be constructed;

- Procurement scheduling, i.e. time table for events such as date of Issue of Bidding Documents, Opening of bids.  Award of contract, Completion of works, etc.;

- Identification of the critical path i.e., the most important contract whose delay will affect the scheduling of other contract packages.

(1.2) 	the procurement plan shall be updated periodically to reflect realities in the implementation.

## 2.	Annual Procurement Plan

Annual Procurement Plan (APP) is the segregation of District Development Plan (DDP) for the procurement of Civil Works, Consulting Services and Goods in the district. The annual procurement plan of Trail Bridges should be made as per master or periodic plan of the district and should be prepared and approved as per Local Self Governance Act (LSGA) and its Regulations.

Primary Considerations given to the annual procurement plan are as follows:

(2.1)	DDC's Office shall plan procurement so that it is carried out within available financial resources and other applicable limitations, and at the most favorable time, and, when possible, in bulk form so as to achieve economies of scale in procurement.

(2.2)	Prior to the commencement of the fiscal year, each DDC's Office shall prepare an Annual Procurement Plan of the procurement that it intends to carry out during that year and submit the plan to the Department of Local Infrastructure and Development of Agricultural Road (DoLIDAR) in connection.  The Annual Procurement Plan shall include information on the:

- types and quantities of the goods, works and services to be procured;

- the timing of the procurement and the implementation of the related contracts;

- an indication of possible packages of procurement, and their value;

(2.3)	Procurement of steel parts for SSTB community bridges should be initiated only after establishment 	of community agreements.

(2.4)	As needed, the DDCs' Office shall periodically update and revise the annual procurement plan.

## 3.	Cost Estimate

During the invitation of bids, the estimate amount shall be made apparent to the firms as per Local Governance Financial Administration Regulations (LGFAR). However, the following considerations shall be noted by the bidders in advance:

i.	The amount thus mentioned is exclusive of the overhead costs.

ii.	The estimated amount shall be considered only as a base line for the preparation of bid; it’s costing, pricing and fixing the final “rate”.

iii.		Any rates thus quoted and approved by the DDC's Office shall be binding upon both the concerned parties, and any request for the change in such rates, whatsoever are the reasons shown by the Firm later on, shall not be entertained.

## 4.	Implementation

### 4.1	Implementation of Short Span Trail Bridge (SSTB) / Community Bridges

A SSTB is basically a Community Bridge. The community initiates, mobilizes resources and manages the construction of the bridge by forming a User’s Committee. The DDC nominates the NGO to support the communities to build SSTB bridges in the district. A detailed engineering survey and detailed design of a SSTB is executed by a nominated NGO. The community manages the construction of the bridge with social organizational and technical support from the NGO.  The DDC provides the “Foreign Materials”, which are not available at or near the construction site to the communities. “Foreign Materials” are steel wire ropes, steel parts and its fixtures, cement, G.I.Wire and tools. Steel wire ropes are procured centrally. Other materials are procured by the DDC.

A SSTB Community Bridges are implemented / constructed as delineated in 4.2 to 4.4 bellow.

#### 4.2	Nomination of NGO

#### (Procurement of Services)

As said in 4.1 above, The DDC needs to nominate the NGO for providing technical and social organizational support to the communities to build SSTB bridges in the district. The Terms of Reference of NGO services shall be as per Trail Bridge Strategy, which is further detailed in the Model Agreement “DDC –TBSSP’ for construction of community bridges. NGO services can be procured under Fixed Budget Contract.  Fixed Budget Contract implies that the rate of service is pre-fixed by the authority concerned (DoLIDAR).

DDC shall prepare a short list of NGOs in 4-6 nos. DDC shall ask short listed NGOs to submit profile and proposal for rendering services. The NGO shall be selected following the criteria given in the Trail Bridge Strategy. The service charge should not exceed the pre-fixed rate but NGOs may submit the financial proposal.

#### 4.3	Procurement of “Foreign Materials”

#### (Procurement of Goods)

The procurement of goods includes procurement of “foreign materials”, i.e. all materials, which are not available at and in the vicinity of the bridge construction site. “Foreign Materials” are wire ropes, steel parts and its fixtures, G.I.Wires, tools and cement.

Cement is to be procured bridge wise to avoid the stock and long storage. Cement shall be procured from reliable outlets (as far as possible from first entry point from the factory and not from small hardware shops) and reputed brand to assure its quality.

Other “foreign materials” are procured through “Fabrication Package” (FP). This package shall include fabrication and supply of steel parts and its fixtures, G.I.Wires and Tools including transportation up to designated points of delivery.

The detail tasks and responsibilities are given in the Terms of Reference (ToR) of Standard Bidding Documents SBD for this procurement package “FP”.

The job is executed by the Fabricator.

#### 4.4	Transportation (Portering), Construction and Bridge Erection

#### (Procurement of Works)

Transportation (portering) of foreign materials from road head to the construction site and all construction and bridge erection works are executed through formation of User’s Committee (UC) from the beneficiaries1. A Collaboration Agreement between the UC and DDC shall be established. UC manages the works with technical and social organizational support of the DDC nominated NGO.

The UC is paid as per official estimated unit rates and actual volume of works. Payment as per “Forced Account” (“Mustroll”) shall not be applied.

# SECTION - II:  PROCUREMENT METHODS

## 5.	Selection of Procurement Method

### 5.1	Community Based Procurement Method

As per Trail Bridge Strategy, a Short Span Trail bridge (SSTB) is basically a Community Bridge. As such, community based implementation and procurement method shall be applied for the construction of SSTB following the approach as described in sub-section 4 of Section – I.

### 5.2	Open Bid Method

A Open Bid system shall be applied for the procurement of “goods” in order to short list capable firms from among many bidders. The objectives of the open bid are:

i.	To avoid tenuous pre-qualification process;

ii.	To discourage the cartel system between the Firms;

iii.	To simplify the process both in terms of time and efficiency

iv.	To promote professionalism regarding the bid and contract management for both concerned parties.

This manual is prepared for the application of open bid procedure only. Open bid method is applied through the open invitation of bid for all eligible and qualified bidders concerned. The bidders can purchase the SBDs without any restrictions from the DDC office and can make their bid within the stipulated time. In order for sufficient number of firms to participate in the bidding process, an Invitation For Bid (IFB) shall be made from eligible firms. Such invitation shall be made on the National Daily Newspaper with all the necessary information.

The DDC's Office shall determine to its satisfaction whether the Bidder that is identified as having submitted the lowest evaluated responsive bid is qualified to perform the contract satisfactorily, in accordance with the criteria listed in Standard Bidding Documents (SBD). The determination shall be based upon an examination of the documentary evidence submitted by the Bidder and its physical verification in accordance with the requirements set forth in the SBD.

#### 5.2.1	Fabrication Package [FP]

This package includes the fabrication and supply of steel parts and its fixtures including quality assurance of the raw materials, fabricated steel parts and fixtures. This package also includes the supply of G.I.Wires and Tools.

The detail tasks and responsibilities of the “FP” are given in the Terms of Reference (ToR) of Standard Bidding Document for “FP”.

#### 5.2.2	Engineering Package [EP]

1.	Third Party Technical Audit.

All the bridges constructed in the district subject to third party technical audit. For detail ToR and selection of consultant refer to “Manual for Consultants” TBS / DoLIDAR.

# SECTION - III:  BIDDING PROCEDURES

## 6.	Bidding Procedures

Bids shall be called from eligible and qualified bidders under Single Envelopes System (SES) and contract shall be signed with the successful bidder for implementation.

Contract management encompasses within it the management and implementation of all activities that are concerned and related with contract in close coordination with the overall planning of DDC, acquiring and filing the necessary BOQs, cost estimates and other relevant documents and publication of bid notice, evaluation of SBD, award of contract, signing of contract agreement, issuing work order and monitoring work executed by the contractors etc. Contract management shall also include quality control/assurance, supervision of overall construction and other related activities.

The procedure to administer any type of contract for any type of work packages within and as defined by the DDC Office, starts from the actual implementation plan or the construction execution in line with the set target according to the overall planning of the DDC and ends when the final account with the Firm/s is settled, the file closed with all the necessary documentation and forwarded for the audit.

Bidding procedures involves all the procedures and steps since the publication of bid notice until completion of the contracted job and final settlement of account including final check, third party technical audit and audit of books and account.

### 6.1	Tender Packages

The packages offered can be of any combination, that is, the package may consist of entirely new construction bridges or major maintenance bridges or any combination of new construction and major maintenance bridges. However, effort shall be made to consider the spatial proximity, common travel route, and the similar nature of work, while preparing a package.

### 6.2	Contract Period

Generally following time limit shall be followed for delivery period.

| Job Type | Target in FY | Delivery Period |
| --- | --- | --- |
| 1. FP | 100 % | 3 months |

However, the Firm has to provide overall planning and compatible work schedule in their technical proposal.

### 6.3	Preparation of Standard Bidding Document (SBD)

The DDC's Office shall use “Standard Bidding Document for the Procurement of Fabricated Steel Parts for Short Span Trail Bridges “SSTB” (second part of this manual).

The information specific to the procurement in hand shall be inserted in the spaces provided in the brackets and italics. Local Development Officer (LDO) prior to publication of the invitation for bid should approve the completed SBD.

#### 6.3.1	Instruction to Bidders (ITB)

  - This ITB section of the SBD provides the information necessary for Bidders to prepare responsive bids in accordance with the requirements of the Employer.  It also gives much information on bid submission, opening and evaluation, and award of Contract. So Fabricators are requested to follow the instructions on this section.

  - Matters governing the performance of the Contractor, payments under the Contract, or matters affecting the risks, rights and obligations of the parties under the Contract are not normally included in this ITB Section, but rather under General Conditions of Contract (GCC) and/or Special Conditions of Contract (SCC).  If duplication of a subject is inevitable in the different sections of the documents, care must be exercised to avoid contradiction between clauses dealing with the same matter.

  - These Instructions to Bidders will not be part of the Contract.

#### 6.3.2	Bidding Data Sheet

  - Section III Bidding Data Sheet (BDS) consists of provisions that complement, supplement or amend the provision of the Instruction to Bidders (ITB). Whenever there is a conflict the provision herein shall prevail over those in ITB Clauses. So specify in detail information or requirements included in this Section and which are specific to each procurement.

  - These provisions shall prevail over the Clauses of the Instructions to Bidders.

  - Instructions for completing the Bidding Data Sheet are provided, as needed, in the notes in italics mentioning the relevant ITB Clauses.

#### 6.3.3	General Conditions of Contract (GCC)

  - The General Conditions of Contract, read in conjunction with the Special Condition of Contract and other documents listed therein, should be a complete document expressing fairly the rights and obligations of both parties.

  - The use of General Conditions of Contract for building and civil works will promote comprehensiveness of coverage, general acceptability of its provisions, savings in cost and time in bid preparation and review, and the development of a solid background of legal case histories.

  - Matters governing the performance of the Fabricators, payments under the Contract, or matters affecting the risks, rights, and obligations of the parties under the Contract are normally included in this section of General Conditions of Contract and/or Special Conditions of Contract.  If duplication of a subject is inevitable in the different sections of the documents, care must be exercised to avoid contradiction between clauses dealing with the same matter.

#### 6.3.4	Special Conditions of Contract (SCC)

- This section of the SBD provides the necessary provisions for contract .

- Special Condition of Contract  consists of provisions that supplement, amend, or specify in detail information or requirements included in General Condition of Contract and which are specific to each procurement. The provisions of SCC that are specific to each procurement can be used changing the provisions over GCC.

- Matters governing the performance of the Contractor/Fabricators, payments under the contract, or matters affecting the risks, rights, and obligations of the parties under the contract are normally included in this section.

- The Special Condition of Contract shall supplement the General Conditions of Contract.  Whenever there is a conflict, the provisions herein shall prevail over those in General Conditions of Contract.  The corresponding clause number in the General Conditions is indicated in parentheses.  Where sample provisions are furnished, they are only illustrative of the provisions that the Employer should draft specifically for each procurement.

### 6.4	Invitation For Bid (IFB)

- Invitation for bid shall be published in the national daily newspaper with all the necessary information as per sample Invitation For Bid. Such an invitation to bid shall be displayed at the office of the DDC's Office, the concerned District Administration Office, Land Revenue Office, DDC, the District Treasury and Comptroller Office and at the Office of construction enterprises or FNCCI; if any, at the head quarters of such district.

- The IFB provides information that enables potential Bidders to decide whether to participate. Apart from the essential items listed in the SBD, the IFB  should also indicate any important Bid evaluation criteria or qualification requirement (for example, a requirement for a minimum level of experience in manufacturing a similar type of goods for which the IFB is issued).

- The IFB should be incorporated into the SBD. The information contained in the IFB must conform to the SBDs and in particular to the relevant information in the Bidding Data Sheet. Sample Invitation for Bid is given in the respective SBD.

- Bids shall not be invited in the basis of percentage premium or discount over the estimated cost.

### 6.5	Distribution of Standard Bidding Documents

- Bidders are required to pay NRs..........for each package of these SBDs. In response to a written request and payment of the cost and postage, the DDC's Office may mail/courier the documents; however the DDC's Office shall not be responsible if the documents are not received in time or not at all.

- However, the competitive bidding is open to any Firm, the bidding document have clearly disclosed the following eligibility requirements applicable to bidder in the procurement proceedings, and the documentation required to prove conformity with those requirements.

- Registered in HMG/N with valid License;

- Tax and VAT registration;

- Firms should be enlisted by Trail Bridge Section/DoLIDAR.

- For CTP, at least previous experience of minimum two successfully completed LSTB type (former SBD type) bridges within last five years are eligible to apply individually.

- For FP, at least previous experience of successfully completed steel parts fabrication of minimum five bridges within last five years are eligible to apply individually.

- However, to encourage the new comers to work and acquire the required experience, they can bid for any such bid, but in a joint venture (JV) with any eligible firms.  In case of a Joint Venture (JV) or support from another firm, a JV agreement or a Memorandum of Understanding (MOU) signed between the concerned parties shall be made available. The leading firm shall be defined and it shall submit its letter of intent in consensus with other firms, if there are any, along with the proposals.

- The details of sale of SBD and submission of the bid shall be recorded in a register maintained for the purpose.  After the expiry of the time for submission of the bids, the Local Development Officer or office employee designated by him shall close the entries having signed it. The account of the revenue obtained from the sale of bids be maintained and shall be deposited in the bank account of District Development Fund (DDF).

### 6.6	Pre-bid Conference

- The DDC's Office will organize a conference on the specified date and place in the bidding document for the purpose of briefing bidders and taking their questions on the SBD, including the technical specifications and other requirements so as to allow bidders to take the information they obtain at the conference into account in preparing their bids. Agenda for pre-bid meeting shall be mainly:

  - Bidding procedures,

  - Schedule of Requirements,

  - Terms of Reference,

  - Other relevant information,

  - Clarification, if any confusion to the bidders.

- The DDC's Office shall prepare minutes of the meeting containing the questions submitted at the meeting and its responses to those questions, without identifying the sources of the questioner.  The minutes shall be provided promptly to all bidders to which the DDC's Office provided the SBD, so as to enable those bidders to take the minutes into account in preparing their bids.

- The  DDC's Office shall issue an amendment to the bidding document if the pre-bid conference or other requests for clarification submitted in writing result in a modification of any technical or commercial aspect of the SBD. The amendment shall be mailed to all those who purchased or received the SBD.

### 6.7	Preparation and Submission of Bid

(1)	The invitation for bid shall provide bidders with a period of at least 30 days from the date of publication to prepare and submit bids.

(2)	Bids shall be submitted in only one place, in accordance with the instructions in the SBD.

- (3)	The bidder shall submit the bid signed, and accompanied by a power of attorney, if so required, and in a sealed envelope, as prescribed in the SBD. Bidders shall submit their technical and financial proposals enclosed in a single envelope.

(4)	The bidder shall have the option to submit the bid by post/mail, courier or personal delivery.  If the bid is delivered by hand, the DDC's Office shall provide a receipt showing the date and time when its bid was received.

(5)	Before the submission of Bid, Firms that are interested to bid shall check in and provide all information required of them as follows:

  - Technical Proposal of the Bid should consist of:

- Bid Form with all forms duly filled

- Technical Proposal as required consisting of:

-	Company profile

-	Recently signed CVs of proposed personnel for the particular work package

-	Equipments

-	Financial status

-	Work program

-	Firm’s Experience in the related field

  - Financial Proposal of the Bid should consist of:

- Bid Form

- Price Schedule

- Bill of Quantities

- List and Weight List of Materials

## 7.	Requirements Applicable to Bid Securities

(1)	Bid security shall be required as specified in the SBD and shall apply only to a specific bid.

(2)	The SBD has specified the amount of bid security, its format and the type of instruments that would be acceptable.

- (3)	The bid security shall be subject to a demand for payment only in the following cases. Such demand should reach in the concerned bank before the expiry of bid security:

  - if the bidder withdraws, or modifies the bid after the bid opening, during its period of validity;

  - does not accept a correction of an arithmetical error; or

  - having been notified of the acceptance of its bid during the validity of the bid, fails to sign the contract if so required or fails to furnish a performance security if so required within the prescribed time limit.

- (4)	Bid securities shall be returned to unsuccessful bidders once the contract is signed.

- (5)	The DDC's Office shall return the bid security amount and document, after whichever of the following that occurs earliest:

- The expiry of validity period of the bid security;

- The termination of the bidding proceedings without the entry into force of a procurement contract;

- The withdrawal of the bid prior to the deadline specified in the SBD.

(6)	The SBD shall require that the bid securities provided by bidders should have a validity period of One Hundred Twenty days from the date of deadline for the submission which is extending for a period Thirty days beyond the expiry of the validity period of bids in order to allow sufficient time to make a demand for payment under the bid security.

## 8.	Bid-validity Period

The SBD shall specify the bid-validity date. Such date shall be 90 days from the deadline of submission of bids. The DDC's Office shall complete the examination, evaluation and comparison of bids and to obtain all the necessary approvals of the proposed award within 90 days from bid opening date.

## 9.	Bid Opening

- (1)	Bid opening shall follow immediately after the closing time for the submission of bids or exceptionally very soon thereafter allowing time for logistics, but in the same day and at DDC Office only.

- (2)	Bids should be opened in the presence of bidders' authorized representatives who choose to attend at the time, date and place specified in the SBD.

- (3)	Bidders' and their authorized representatives alone shall be allowed to be present and shall sign the record to ensure that the data have been read out and recorded correctly,

- (4)	Bids shall be segregate in a following manner:

(a)	Late bids

(b)	Modification envelope

(c)	Withdrawal envelope

- (d)	Bids received in time

- (5)	Bids for which an acceptable notice of withdrawal has been submitted shall not be opened.

- (6)	All bids received prior to the deadline for submissions shall be opened.

- (7)	At the opening, the committee shall open first envelopes marked "Withdrawal" and "Modifications" and all bids received prior to the deadline for submissions and read out the name and address of the bidder, the bid price, discounts if any,

(8)	Any other important infirmity noticed shall be announced and recorded in the minutes which shall be signed by those present such as:

- the presence or absence of a bid security;

- discrepancy between figures and words,

- absence of signature, unsigned corrections,

- any other material deviation from the SBD.

- (9)	The read out matter shall be circled.

(10)	The committee shall prepare minutes (MUCHULKA) of the bid-opening proceeding, which shall contain the information read out at the bid-opening and be signed by all those present.

(11)	No decision as to the acceptance or rejection of any bid shall be taken or announced in the bid opening session.

# SECTION - IV:  BID EVALUATION

## 10.	Bid Evaluation

The main purpose of bid evaluation is to determine the lowest evaluated bid among the bids submitted before the bid closing time on the date specified in the SBD.  The lowest evaluated bid may or may not necessarily be the lowest priced bid.  In order to determine accurately the lowest evaluated bid in accordance with the terms and conditions of the SBD.

Following principles and practices in bid evaluation must be clearly understood and observed in the bid evaluation process:

a)	Confidentiality of Procedures

After the public opening of bids, no information relating to the examination, clarification and evaluation of bids, and recommendations concerning awards, shall be communicated to any person not officially concerned with these procedures until the announcement of the award of the contract to the successful Bidder has been made.

b)	Clarifications of Bids

Clarifications, which do not change the substance or price of the bid, may be requested or accepted by DDC's Office. The request for clarifications and the response by the Bidder shall be in writing or by fax (the term "fax" is deemed to include electronic transmission such as facsimile, email, cable and telex).  Any response to an inquiry, which leads to a change in the bid price shall be considered as an alteration and shall not be considered in the bid evaluation.  The records of all clarifications sought and received must be kept.

c)	Rejection of Bids

All valid bids received shall be evaluated in accordance with the terms and conditions of the SBD and only those bids which do not substantially meet the Schedule of Requirements or the bidding requirements will be rejected.

d)	Extension of Bid Validity Period

The DDC's Office shall make every effort to complete bid evaluation and contract award before the expiration of bid validity.  The validity of bids may only be extended in exceptional circumstances.  If, prior to the expiry of the validity period of bids the DDC's Office feels that additional time will be required to complete all steps and notify an award, it should request all responsive bidders to extend the validity by the minimum period required to do so. For extension of bid validity prior concurrence of the WB/IDA or ADB (whichever is applicable) through PCU of RAIDP/DRILP (whichever is applicable) is required for the first request for extension if it is longer than 8 weeks and for all subsequent requests for extension irrespective of the period.

Bidders who are willing to extend the validity of their bids shall not be permitted to modify the substance or price of their bids.  Extension of validity is a decision of the bidder. A refusal to extend the bid-validity period shall not result in forfeiture of the bid security.  Extension of the bid-validity period shall, however, be subject to extension of the bid security if one was required in the first place.  Without such an extension of the bid security, a bid shall be deemed not extended.

e)	Rejection of All Bids

The rejection of all bids is justified when the bids submitted are not responsive or where none of the bids received meets the Schedule of Requirements or where there is evidence of lack of competition, or where all bid prices have substantially exceeded the cost estimate.

### 10.1	Reception and Security of Bids

- (1)	The DDC's Office shall receive bids and keep them in a secured manner that does not permit the bids to be opened by accident or viewed and handed over to the bid opening committee at the bid opening time.

(2)	Prior to opening of bids, disclosure of the number of the bids received shall be made only to public officials who as part of their official duties require that information.

### 10.2	Rejection of Late Bids

(1)	A bid received by the DDC's Office after the deadline for the submission of bids shall not be opened and shall be returned to the bidder that submitted it after noting the date and time of arrival.

### 10.3	Bid Evaluation Committee

Bidder’s Envelope containing Application Form, Technical Proposal and bid documents will be evaluated by a committee consisting as per LFAR but including minimum of below listed personnel.

-	DDC Engineer

-	DDC Accountant

-	Representative of Donor Agency, if applicable

### 10.4	Bid Evaluation Procedure

Bids should be evaluated to determine the lowest evaluated bid strictly in accordance with the terms, conditions and schedule of requirements stipulated in the SBD.

Further, the evaluation procedure shall provide fairness to all Bidders as it will produce a transparent, fair and accurate outcome of the bidding.  There are four distinct stages in the bid evaluation process, which should be followed in a logical sequence.

### 10.5	Preliminary Examination for Completeness of Bids

The purpose of this step is to examine whether the bids received were complete as required by the SBD before further detailed evaluation.  The areas to be covered by the examination are:

Examination for Completeness of Bids

| Completeness requirements | Name of bidder |  |  |  |  |  | Name of bidder |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Bidder 1 |  | Bidder 2 |  | Bidder 3 |  | Bidder 4 |  | Bidder 5 |  | Bidder 6 |  |
|  | Yes | No | Yes | No | Yes | No | Yes | No | Yes | No | Yes | No |
| 1. Bid form was purchased from the concerned DDC's office |  |  |  |  |  |  |  |  |  |  |  |  |
| 2. The person or firm submitting the bid purchased the bid form |  |  |  |  |  |  |  |  |  |  |  |  |
| 3. The bid is sealed |  |  |  |  |  |  |  |  |  |  |  |  |
| 4. Bid documents are properly signed by the bidder or authorized representative |  |  |  |  |  |  |  |  |  |  |  |  |
| 5. A power of attorney for the authorized persons is submitted, if authorized representative has signed the bid |  |  |  |  |  |  |  |  |  |  |  |  |
| 6. Bid security as specified in the SBD is submitted |  |  |  |  |  |  |  |  |  |  |  |  |
| 7. Joint venture agreements are submitted, if joint venture proposed |  |  |  |  |  |  |  |  |  |  |  |  |
| 8. Registered in HMG/N with valid License |  |  |  |  |  |  |  |  |  |  |  |  |
| 9. Tax and VAT registration |  |  |  |  |  |  |  |  |  |  |  |  |
| 10. Enlisted by Trail Bridge Section/DoLIDAR |  |  |  |  |  |  |  |  |  |  |  |  |
| 11. For “FP”, at least previous experience of successfully completed steel parts fabrication of minimum five bridges within last five years |  |  |  |  |  |  |  |  |  |  |  |  |

#### 10.5.1	Determination of Responsiveness of Bids

The scrutiny of bids for responsiveness to the provisions of the SBD is one of the most important aspects of the evaluation of bids.  If a bid fails to meet any of the above tests, it shall be rejected and excluded from further consideration.  Those bids that contain minor deviations or reservations, but that may be considered responsive, shall be included in the detailed evaluation and comparison of bids.

#### 10.5.2	Clarification of Bids

In the process of evaluation, Bidders may be requested to provide clarifications of their bids where such clarifications are deemed necessary.  Bidders are not permitted, however, to change the substance or price of their bids.  The records of all clarifications sought and received must be kept by DDC's office for bid evaluation.

#### 10.5.3	Correction of Arithmetical and Computational Errors

(1)	The Bid Evaluation Committee shall correct any arithmetical errors appearing on the face of the bid, or in the bill of quantities, and inform the bidder in question of the correction.  If the bidder refuses the correction, the bid shall be rejected and the bid security is thereby subject to forfeiture.

(2)	If there is a discrepancy between the unit price and the line item total that is obtained by multiplying the unit price and quantity, the unit price shall prevail and the total price shall be corrected.

(3)	Where there is a discrepancy between the amounts in figures and in words, the amount in words shall govern.

#### 10.5.4	Detailed Technical Evaluation of Responsive Bids (Technical Proposal)

Following the preliminary examination of bids, the DDC's Office shall proceed to the detailed evaluation and comparison of the bids that have not been rejected in the preliminary examination stage. In order to ensure that a thorough check of the responsiveness of all bids is carried out, a Table of Responsiveness to Technical Requirements should be prepared.  The tables should list all major conditions for Technical Requirements, which the Bidders must meet for their bids to be considered responsive.  The responsiveness of each bid received should then be checked against this list and its conformance to each item should be entered in the tables.  All bids must be checked for responsiveness to the schedule of requirements (evaluation criteria) of the SBD based on bidder’s technical proposal.  Bid not conforming to schedule of requirements (not qualified) shall be rejected.

Detailed Technical Evaluation of Responsive Bids

Fabrication Package ( FP)

(Technical Proposal)

| Technical and Financial requirements | Minimum Required | Name of Bidder |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Bidder 1 |  | Bidder 2 |  | Bidder 3 |  | Bidder 4 |  | Bidder 5 |  | Bidder 6 |  |
|  |  | Yes | No | Yes | No | Yes | No | Yes | No | Yes | No | Yes | No |
| 1. Work Experience | Fabrication Work of minimum 5 trail bridges |  |  |  |  |  |  |  |  |  |  |  |  |
| 2. Equipments | Saws ….…….. 2 nos. |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Drilling Machine …….…… 2 nos. |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Welding Machine with Voltage Stabilizer ………… 2 nos. |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Grinders ……..…… 2 nos. |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Lathe Machine …….…… 1 nos. |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Gas cutting equipment ….……… 2 nos. |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Blacksmith Shoo …….…… 1 no. |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Galvanizing Plant- Own/Sub-letting |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Installed Temperature meter ………… 1 no. |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Hydrometer ……..… 3 nos. |  |  |  |  |  |  |  |  |  |  |  |  |
|  | PH-Meter …….…. 2 nos. |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Adhesion Testing Hammer ………… 1 no. |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Zinc Coat Measuring Instrument …………. 1 no. |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Weighting Machine ………… 1 no. |  |  |  |  |  |  |  |  |  |  |  |  |
| 3. Personnel | Workshop Engineer ………… 1 per. with experience of minimum three years in trail bridge steel parts fabrication |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Foreman/Overseer/Mechanics ………. 2 persons. with experience of minimum three years in trail bridge steel parts fabrication |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Skilled/Semi-skilled labourers ……….... 10 persons. |  |  |  |  |  |  |  |  |  |  |  |  |
| 4. Financial | Liquid Assets amount of NRs. 8,00,000.00. |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Bonding Capacity amount of NRs. 5,00,000.00. |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Net Worth amount of NRs. 20,00,000.00 |  |  |  |  |  |  |  |  |  |  |  |  |

#### 10.5.5	Evaluation of Financial Proposal

Among the bidders whose technical proposals fulfills the schedule of requirements, the lowest evaluated bid shall be awarded the contract to execute the said work. The financial evaluation of bids involves the determination of the cost to the DDC's Office of each bid so that it may select the bid with the lowest cost, though not the lowest price. Such evaluation of each bid shall be carried solely in accordance with the criteria and methodology disclosed in the SBD.

#### 10.5.6	Determination of Lowest Evaluated Responsive Bid

After completing the above evaluation, and comparing the evaluated cost of each bid, the lowest evaluated responsive (qualified) bid shall be determined in accordance with the provisions of the SBD.

Post-bidding negotiations shall not be allowed with the lowest evaluated bidder or any other bidders.

#### 10.5.7	Confidentiality of Bid Evaluation

Information relating to the examination, clarification, evaluation and comparison of bids shall not be disclosed to bidders or to any other person not involved officially in the process or in the decision on which bid should be accepted, except as provided in the LFAR.

#### Rejection of Bids and Re-bidding

The fact that there may be only a few responsive bids, or even only one, shall not be a ground for rejection or re-bidding if the bid price is competitive. Bids shall not be rejected merely on the basis of a comparison with an official estimated cost. Reason for high bidding shall be examined in case of lowest evaluated bid is substantially high.

Re-bidding shall be made only in case of:

    - all bids are non responsive; or

    - the investigation reveals that the lowest evaluated bid is substantially above the cost estimate without any substantial reasons; or

    - if it is concluded that there is collusion among the bidders.

For re-bidding prior concurrence of the WB/IDA or ADB (whichever is applicable) through PCU of RAIDP/DRILP (whichever is applicable) is required.

# SECTION - V:  Contract Management

## 11.	Notification of Award

(1)	Following the identification of the lowest evaluated responsive bidder the DDC's Office provide notification of award of the contract to the successful bidder in writing.

(2)	Award of the contract shall be made within the validity period of the bid.

## 12.	Performance Security

Performance security equivalent to 5% of contract amount shall be required. Initial validity period for performance bond should be minimum 12 Months for “FP”.

Contractor’s Performance Security shall apply only to the specific contract under which it was furnished. Performance Security shall be in original form.

## 13.	Contract Award

The successful bidder should be present within the time thus stipulated to enter into legal commitment by signing an agreement. The Firm should provide the Employer with a performance security either in the form of a Bank voucher of a deposit in the specified Bank A/C or in the form of a valid performance security issued by an authorized Bank in favor of DDC’s  Office,……  ……… prior to signing the agreement.

Upon submission of performance security by the Firm the office shall immediately process the document and make arrangement for signing the Agreement. In the event of a failure of the bidder whose bid has been accepted to sign a contract in accordance with the SBD, to provide security for the performance of the contract, the DDC's Office shall select a successful bid in accordance with the evaluation criteria set forth in the SBD from among the remaining bids that are in force.

Split award or lottery in award of contracts shall not be carried out.  When two or more bidders quote the same lowest price, an investigation shall be made to determine any evidence of collusion, following which;

a)  if collusion is determined, the parties involved shall be disqualified and the award shall then be made   to the next lowest evaluated and qualified bidder and

b)  if no evidence of collusion can be confirmed, then fresh bids shall be invited.

For re-bidding prior concurrence of the WB/IDA or ADB (whichever is applicable) through PCU of RAIDP/DRILP (whichever is applicable) is required.

### 13.1	Contract Limit

Irrespective of whatsoever have been said earlier, the number of contracts which can be offered to any one Contractor is limited to 3 in numbers of bridges in one fiscal year.

### 13.2	Witness

From DDC’s Office witness for Contract Agreement shall be DDC Engineer and the Accountant.

## 14.	The Services

The services for the packages described in Instruction to Bidder under these Contracts in accordance with the Terms of Reference, Technical Specifications, Design Drawings and Quality Assurance Document set forth herein shall be performed professionally and accurately by the Firm.

## 15.	Commencement Date

Services shall be commenced not later than seven days after the Employer notifies the Firm to proceed with the work. On the contrary case, if the firm does not commence work within aforesaid time without any reasonable cause, the contract may be terminated by the Employer.

## 16.	Orientation

An orientation program to the Firm, to whom job was awarded, shall be conducted by the Employer. The main objectives of the orientation program shall be to brief the Firm about the Scope of Works and ToR, methodology and quality requirements

## 17.	Execution of Work

(SSTB Community Bridges)

17.1	Fabrication of Steel Parts

The job is executed by the Fabricator. The quality assurance of the fabricated steel parts including raw materials all complete is the sole responsibility of the respective Fabricator following the standard “Quality Assurance Document” included in the SBD and must meet the required standards and fulfill the quality requirements and specifications.

However, from Employer’s side supervision and quality control of fabrication of bridge steel parts shall be performed by the NGO nominated by the DDC's office following the “Quality Control Manual for Trail Bridges”.

17.2	Portering (Transportation), Construction and Bridge Erection

Portering (transportation), construction and bridge erection is executed through UC following the roles and responsibility as per Agreement between DDC and UC.  The NGO shall provide the technical, social/organizational and managerial support to the UC for the execution of the job.

## 18.	Technical Support, Quality Monitoring, Inspection and Acceptance

(SSTB Community Bridges)

Over all quality monitoring of all work has to be performed through the NGO as per “Quality Control Manual for Trail Bridges”.

### 18.1	Inspection and Quality Control of Steel Parts

Inspection of fabricated steel parts, fixtures and G.I.Wires is to be done though the NGO assigned by the DDC as per “Quality Control Manual for Trail Bridges”.

If the steel parts are found fabricated not accordingly during inspection, an “Instruction Form” for Steel parts has to be filled up by the Inspector with details of correction/replacement required. If steel parts are found to be completed and as per design drawings and technical specifications an ‘Inspection Certificate” is to be issued.

The work performed by the NGO shall be checked by the DDC’s Engineer, make suggestions / recommendations where necessary to the satisfaction of the Employer. Final acceptance of the fabrication of the steel parts and other “foreign materials” shall be issued by the Inspecting NGO and endorsed by the DDC’s Office. Certification of funding agency is also required for final acceptance.

In addition, Quality Assurance Documents maintained by the Fabricator are also to be submitted to the Employer.

### 18.2	Technical Support and Quality Control of Construction &                        Bridge Erection Works

Transportation (portering) of “foreign materials “ from road head to the construction site, construction and bridge erection works are executed through UC following the roles and responsibility as per Collaboration Agreement between DDC and UC.  The NGO shall provide the technical, social / organizational and managerial support to the UC for the execution of those works. The responsibility of quality of executed works solely lies on the support providing NGO. NGO shall assure that the work executed are as per the technical specifications, norms/standards and design drawings.

## 18.2.1	Work Completion Report (WCR)

After completion of the bridge, the respective NGO provides the WCR to the DDC’s Office. In response to the WCR submitted by the NGO, final inspection of the completed bridge shall be done jointly by representative of DDC, NGO and funding agency5.

## 18.2.2	Work Completion Certificate (WCC)

In response to the WCR submitted by the NGO, final inspection of the completed bridge shall be done jointly by representative of DDC, NGO and funding agency5 as per Final Inspection Checklist of “Quality Control Manual for Trail Bridges” within 15 days of date of submission of WCR. If the quality of completed bridge is found good as per design, norm/standard and technical specifications, WCC is issued to the UC.

If the work quality is not to the satisfaction or some works are incomplete or imperfect, the joint final inspection team shall issue the final inspection report with description of all incomplete, imperfect and unacceptable works. The NGO shall support the community to rectify and complete the entire job as per final inspection report within the stipulated time. Only after completion of all incomplete, imperfect and unacceptable works, a WCC shall be issued. However, accountability for such imperfect and unacceptable works remains with the NGO.

## 19.	Payment Procedures

### 19.1	Advance

Regarding any advances to be made available to any firms it shall be governed by LFAR/HMG fiscal rule that up to 20% advance of contract amount can be provided against Bank Guarantee valid up to the recovery of such advance, if provision is made in the Agreement and the Firm request for it in writing.

### 19.2	Payment

Payment for work done shall be according to the “Mode of Payment” mentioned in the “Condition of Contract”.  Provision for advances shall be governed by the LFAR, accepted practice and the contract documents.

### 19.3	Place of Payment

Payment for all contract packages shall be done at DDC’s Office.

## 20.	Notice of Delay

In the event that the Firm encounters a delay in obtaining the required services and facilities set forth for the provision of service, the Firm shall promptly notify the Employer of such delay with documentary evidence and may request for time extension for completion of the project before expiry of the stipulated time.

## 21.	Time Extension

Time extension will be granted according to prevailing fiscal rules of LFAR only if the reasons are acceptable to Employer.

## 22.	Penalties for Delay

In case of reported delays in the performance of the service beyond the specified time of completion due to Firm’s default, the penalty will be determined on the basis of prevailing LFAR.

## 23.	Settlement of Disputes

Any dispute or difference arising out of the Contract which can not be amicably settled between the parties shall be finally settled under the prevailing rules of arbitration and litigation in Nepal.

## 24.	Third Party Technical Audit

A technical audit by the independent consultant (other than those involved in survey/design or supervision and quality control) shall be made for all constructed bridges of the districts as per respective ToR for Third Party Technical Audit. A technical audit shall evaluate the overall quality of survey/design, and the quality of constructed bridge and cost of the bridge.

# SECTION - VI:  Miscellaneous

## 25.	Internal DDC Contract Management Procedure Table

| S. N. | Job type | Bill Sub- mission | Reporting & Checking | Payment Procedure | Approval of payment | Payment at | Quality Control and Monitoring |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1. | FP | Firm | DDC Engineer | Account Section | Chief, DDC’ Office | DDC’s Office | DDC Appointed NGO |

## 26.	Record Keeping Requirements

(1)	DDC's Office shall open a special file for every procurement proceeding.  All the documentation relating to the proceeding such as the invitation to bid, decision of award, work take-over certificate and any other information on the method of the Supplier's completion of his commitment shall be kept in the file.  A contract file index shall be established for each contract file.

(2)	Contract files shall include, at a minimum, the following documentation:

- contract file index;

- invitation to bid,

- SBD;

- requests for clarification and responses thereto, and record of circulation of responses to all participating bidders;

- minutes of pre-bid meeting with bidders

- minutes of bid opening;

- bids;

- bid evaluation report

- documentation of requests for and responses to clarifications of bids;

- copies of notice of acceptance sent to winning bidder;

- procurement contract;

- minutes of orientation meeting with successful bidders;

- documentation related to contract implementation, including progress reports, invoices and other documents such as inspection reports and any supporting documentation;

- documentation related to change orders and contract modification ,if any;

- documentation related to inspections, acceptance and receiving, including any exercise of the DDC's Office’s right to reject defective performance;

- copies of all correspondence with the Supplier;

- requests to subcontract and responses thereto; and the record of the procurement proceedings, as well as all of the documentation referred to therein

Refer to “Social Organizational Support Manual” / TBS, DoLIDAR

Wire Ropes shall be provided by SDC/Helvetas for RAIDP and DRILP program

Refer to Standard Bidding Document for “FP” (second part of this Manual).

Refer model “Collaboration Agreement” between the UC and DDC

TBSSP/Helvetas on behalf of Donor as part of TA.