Section - VIII

Terms of Reference

Table of Clauses:

1.	Objective	63

2.	Scope of Work	63

2.1	General	63

2.2	Fabrication of Steel Parts	63

2.2.1	Qualioty Managment and Quality Assurance	63

2.3	Construction	64

2.3.1	Transportation and Construction	64

2.3.2	Supervision and Quality Assurance	64

2.4	Reports	64

2.4.1	Fabrication	65

2.4.2	Construction	65

2.5	Communication	65

3.	Services and Facilities Provided by the Employer	66

Section - VIII

Terms of Reference (ToR)

# 1.	Objective

The Employer intends to implement and supervise the execution of fabrication, transportation, construction and erection of LSTB bridges on main trails and strategic crossings.  The work is intended to be procured by utilising the services of private eligible Contractors with support of  Fabricators.

2.	Scope of Work

## 2.1	General

The Contractor / Fabricator shall perform the above mentioned and herein described job professionally with accepted level of accuracy, existing engineering practice, and sound judgement based on experience and professional ethics.

## 2.2	Fabrication of Steel Parts

It consists of followings:

- Procurement  of raw materials as per specification  for fabricating steel parts,

- Procurement of  fixtures, i.e. nuts & bolts, thimbles, buldoggrips etc.  according to the specifications;

- Provide samples of raw material to the Employer for lab testing

- Fabrication of steel parts  according to specification and drawings;

- Galvanisation of fabricated steel parts according to the specification;

- Galvanization of steel parts (refer to specification for galvanization) is permitted only at the plants, which  have complete process and setup (enlisted by Trail Bridge Section, DoLIDAR);

- Transportation of fabricated bridge parts from workshop to galvanisation plant and back to workshop or to the specified point of delivery;

### 2.2.1	Qualioty Managment and Quality Assurance

- Maintain in- built quality management quality assurance system with necessary equipement/tools and measuring instruments. This system shoul cover from quality of raw material up to galvanization and the final product;

- Continuous supervision and quality management during fabrication and galvanization according to the specification for steel works by a competent personnel;

- Maintain quality assurance documentation as per given format in Annex C:Quality Assurance Document;

- Arrange inspection of completed bridge parts by Authorised Inspecting Engineer appointed by the Employer.

## 2.3	Construction

### 2.3.1	Transportation and Construction

- Construction (or acquiring by  hiring it) of the camp, its operation & maintenance;

- Layout of bridge;

- Transportation of bridge parts, and procurement and transportation of materials such as cement, gabion etc. up to bridge construction site;

- Collection of materials such as sand, gravel, boulders etc.;

- Acquire wire rope from the Employer and blasting materials and transport to sites;

- Civil construction works of anchorage blocks and bridge foundations, protection work, consisting of concrete, masonry, retaining wall (gabion crates/ block stone masonry),etc.;

- Mechanical works such as  tower erection, cable hoisting, walkway  and fitting of other parts, windguy arrangements,;

- Finishing works such as, rust prevention by putting coaltar on saddles, cables near saddles, and all non-galvanised threads, and environmental restoration of the construction scar by sowing grass, turfing, afforestation, construction of wicker work fences etc.

- Continuous supervision and quality management during transportation, construction and bridge erection  according to the specification for these  works by a competent personnel 
(see below 2.3.2);

- Arrange inspection at pre-defined critical stages of construction and bridge erection (1.Bridge Layout & Foundation Excavation, 2. Masonry / Concrete Works and placing of Anchorage Parts, 3.Tower Erection, cable hoisting, 4.Final Check) by Authorised Inspecting Engineer appointed by the Employer.

2.3.2	Supervision and Quality Assurance

- Employ and manage all necessary staff for continuous site  supervision;

Supervising staff should be at least civil overseer with required qualification;

- Layout of bridge (within 7 days after receiving work order from the Employer);

- Supervise all civil construction work including quality control according to technical specification;

- Supervise all mechanical/erection  and finishing works including its quality control / assurance;

- Inspect all material and workmanship including testing of materials, wherever necessary, by an engineer;

- Provide test certificates of steel sections intended to  use for fabrication, G.I. Wire for wire mesh, gabion works and cement;

- Maintain quality assurance documentation strictly as per given format and instructions
as per Annex C: Quality Assurance Document.

## 2.4	Reports

Following reports for different phases have to be submitted to the Employer by the Contractor/Fabricator, besides those already specified and provided with standard formats.  They shall be concise and transparent with photographic evidence of the completed quality work.

### 2.4.1	Fabrication

a)	Procurement and stock of raw materials for fabricating bridge parts;

b)	Test Certificates of raw materials (steel sections, zinc purity),  fixtures (nuts/bolts, buldoggrips etc)

b)	Progress in fabrication of bridge parts (i.e. anchorage parts, tower parts, walkway and steel deck);

c)	Progress in galvanisation of fabricated bridge parts;

d)	Completion of fabrication and galvanisation work, inspection of the completed works by the Authorised Inspecting Engineer appointed by the Employer;

e)	A final report detailing the experience of the Firm during this phase including problems encountered in liaison with the Employer (its critical review).

All above mentioned reports shall be submitted in a monthly basis.

### 2.4.2	Construction

a)	General impressions of the bridge location/site, its surrounding environment, and others, including problems encountered;

b)	Technical aspects and problems encountered during layout and a statement of whether the survey and design components of the bridge fits with real site conditions;

c)	Progress of works (i.e., 1. Transportation of materials, 2. Bridge Layout & Foundation Excavation, 
2. Masonry / Concrete Works and Placing of Anchorage Parts, 3.Tower Erection, Cable hoisting, 
4.  Hoisting of Windguy Arrangements etc.);

d)	Completion of construction and bridge erection works, inspection at different stages of the completed works by the Authorised Inspecting Engineer appointed by the Employer;

e)	A final report detailing the experience of the Contractor/Fabricator including problems encountered in liaison with the Employer (critical review).

All above mentioned reports are to be submitted in a monthly basis.

## 2.5	Communication

a)	The reports shall be sent to the Employer either by :

i)	Firm’s staff travelling from site to Kathmandu

ii)	Employer’s staff on inspection tours

iii)	By registered mail or fax

b)	Notice or report will be deemed to be effective as follows :

i)	In case of personal delivery and  registered mail, on their delivery

ii)	In case of fax, 24 hours following confirmed transmission

c)	The quality control is inherently associated with Employer's Engineer (authorized Inspecting Engineer appointed by the Employer). Communication plays a vital role in systematic execution and timely completion of work.

i)	Copies of monthly report has to be provided to Employer's Engineer

ii)	Employer's Engineer has to forward with timely comments any communications to the Employer’s office.

iii)	Key supervisions, timely checks and approvals shall be duly communicated.

The whole communication framework shall be according to the Quality Control/Assurance Manual.

# 3.	Services and Facilities Provided by the Employer

The Employer provides free of cost one copy each of the  following documents and matreials:

a)	Fabrication Drawings

-	1 set of steel drawings

-	1 set of Schedule of Works (SoW)

b)	Construction Drawings

-	1 set Construction Drawings including General Arrangement

-	1 set of Schedule of Works (SoW)

-	1 set Site Instruction Book

-	1 set Site Inspection and Work Completion Certificate (only for reference)

-	Set of standard formats for reporting

b)	Materials

-	Wire Ropes

Contractor should collect the Wire Ropes from the DDC’s/or Central Store