Section - IV

GENERAL CONDITIONS OF CONTRACT (GCC)

Table of Clauses:

A.	General	20

1.	Definitions	20

2.	Interpretation	21

3.	Language and Law	21

4.	Project Manager’s Decisions	21

5.	Delegation	21

6.	Communications	22

7.	Subcontracting	22

8.	Other Contractors	22

9.	Personnel	22

10.	Skilled/Unskilled Labour	22

11.	Risks	22

12.	Contractor’s Risks	22

13.	Insurance	22

14.	Site Investigation Reports	23

15.	Queries about the Special Condition of Contract	23

16.	Contractor to Construct the Works	23

17.	The Works to be Completed by the Intended Completion Date	23

18.	Approval by the Project Manager	23

19.	Safety	23

20.	Discoveries	23

22.	Access to the Site	23

23.	Instructions	24

24.	Disputes	24

25.	Procedure for Disputes	24

26.	Replacement of Adjudicator	24

B.	Time Control	24

27.	Program	24

28.	Extension of the Intended Completion Date	24

29.	Acceleration	25

30.	Delays Ordered by the Project Manager	25

31.	Management Meetings	25

32.	Early Warning	25

C.	Quality Control	25

33.	Quality Control	25

34.	Quality Assurance	26

35.	Identifying Defects	26

36.	Tests	26

37.	Correction of Defects	26

38.	Uncorrected Defects after Completion Date	26

D.	Cost Control	26

39.	Design, Drawing and Schedule of Works	26

40.	Variations	27

41.	Payment Certificates	27

42.	Payments	27

43.	Compensation Events	27

44.	Tax	28

45.	Retention	28

46.	Liquidated Damages	28

47.	Advance Payment	28

48.	Performance Securities	29

49.	Cost of Repairs	29

E.	Finishing the Contract	29

50.	Completion	29

51.	Taking Over	29

52.	Final Account	29

53.	Termination	29

54.	Payment upon Termination	30

55.	Property	30

56.	Suspension of Donor Agency Loan/Credit/ Grant	30

F.	Additional Clauses	31

57.	Project Manger’s Duties and Authority	31

58.	Quarries and Spoil Dumps	31

59.	Safety, Security and Protection of the Environment	31

60.	Value Added Tax	31

61.	Income Taxes on Staff	32

62.	Duties, Taxes and Royalties	32

63.	Member of Government, etc, not Personally Liable	32

64.	Approval of Use of Explosives	32

65.	Compliance with Regulations for Explosives	32

66.	Permission for Blasting	32

67.	Records of Explosives	32

Section - IV

General Conditions of Contract (GCC)

# A.	General

| ## 1. Definitions | 1.1 Boldface type is used to identify defined terms. - The Adjudicator is the person appointed jointly by the Employer and the Contractor to resolve disputes in the first instance, as provided in Clauses 24 and 25 hereunder. - Compensation Events are those defined in Clause 43 hereunder. - The Completion Date is the date of completion of the Works as certified by the Project Manager, in accordance with Sub-Clause 50.1. - The Contract is the Contract between the Employer and the Contractor to execute, complete, and maintain the Works. It consists of the documents listed in Clause 2 below. - The Contractor is a person or corporate body whose bid to carry out the Works has been accepted by the Employer. - The Contractor’s bid is the completed Bidding documents submitted by the Contractor to the Employer. - The Contract Price is the lump sum price to execute complete and maintain the works on turnkey mode of contract stated in the Notification of Contract Award and thereafter as adjusted in accordance with the provisions of the Contract. - Days are calendar days; months are calendar months. - A Defect is any part of the Works not completed in accordance with the Contract. - The Defects Liability Certificate is the certificate issued by Project Manager upon correction of defects by the Contractor. - The Defects Liability Period is the period named in the SCC and calculated from the Completion Date. - Drawings include calculations and other information provided or approved by the Project Manager for the execution of the Contract. - The Employer is the party who employs the Contractor to carry out the Works. - Equipment is the Contractor’s machinery and vehicles brought temporarily to the Site to construct the Works. - The Initial Contract Price is the Contract Price listed in the Employer’s Letter of Acceptance. - The Intended Completion Date may be revised only by the Project Manager by issuing an extension of time or an acceleration order. - Materials are all supplies, including consumables, used by the Contractor for incorporation in the Works. - The Project Manager is the person named in the SCC (or any other competent person appointed by the Employer and notified to the Contractor, to act in replacement of the Project Manager) who is responsible for supervising the execution of the Works and administering the Contract. - The Site is the area defined as such in the SCC. - Site Investigation Reports are those that were included in the Bidding documents and are factual and interpretative reports about the surface and subsurface conditions at the Site. These reports also include those reports which are prepared for construction material sources. - Specification means the Specification of the Works included in the Contract and any modification or addition made or approved by the Project Manager. |
| --- | --- |

|  | v) The Start Date is given in the SCC. It is the latest date when the Contractor shall commence execution of the Works. It does not necessarily coincide with any of the Site Possession Dates. w) A Subcontractor is a person or corporate body who has a contract with the Contractor to carry out a part of the work in the Contract, which includes work on the Site. x) Temporary Works are works designed, constructed, installed and removed by the Contractor that are needed for construction or installation of the Works. y) A Variation is an instruction given by the Project Manager, which varies the Works. z) The Works are what the Contract requires the Contractor to construct, install and turn over to the Employer, as defined in the SCC. |
| --- | --- |
|  | aa) The Services means the works described in the Terms of References to be performed by the Contractor including modification, alteration and additions of works and other obligations of the Contractor covered under the Contract. bb) Engineer or The employer's representative means the engineer appointed by the Employer (Employer's nominated Consultant) from time to time and notified to the Contractor in writing. cc) Terms of Reference (TOR) means the schedule of works and duties, defined by the bidding document and to be executed under this contract. |
| ## 2. Interpretation | 2.1 In interpreting these Conditions of Contract, singular also means plural, male also means female or neuter, and the other way around. Headings have no significance. Words have their normal meaning under the language of the Contract unless specifically defined. The Project Manager will provide instructions clarifying queries about these Conditions of Contract. 2.2 If sectional completion is specified in the SCC, references in the Conditions of Contract to the Works, the Completion Date, and the Intended Completion Date apply to any Section of the Works (other than references to the Completion Date and Intended Completion Date for the whole of the Works). 2.3 The documents forming the Contract shall be interpreted in the following order of priority: - Agreement, - Letter of Acceptance, - Contractor’s bid, - Special Condition of Contract (SCC), - General Conditions of Contract (GCC), - Terms Of References (TOR) - Technical Specification, - Design and Drawings, - Schedule of Works (SOW), and - Any other document listed in the SCC as forming part of the Contract. |
| ## 3. Language and Law | 3.1 The language of the Contract and the law governing the Contract are stated in the SCC. |
| ## 4. Project Manager’s Decisions | 4.1 Except where otherwise specifically stated, the Project Manager will decide contractual matters between the Employer and the Contractor in the role representing the Employer fairly and impartially. |
| ## 5. Delegation | 5.1 The Project Manager may delegate any of his duties and responsibilities to other people, except to the Adjudicator, after notifying the Contractor, and may cancel any delegation after notifying the Contractor. |

| ## 6. Communications | 6.1 Communications between parties that are referred to in the Conditions of Contract shall be effective only when in writing. A notice shall be effective only when it is delivered. |
| --- | --- |
| ## 7. Subcontracting | 7.1 The Works/Services shall be fully discharged by the accredited contractor and shall strictly abstain from sub-contracting in whole or any portion of the Works Services to any other firm other than the fabrication work and joint venture partners mentioned in Technical proposal. |
| ## 8. Other Contractors | 8.1 The Contractor shall cooperate and share the Site with other contractors, public authorities, utilities and the Employer between the dates given in the Schedule of Other Contractors, as referred to in the Special Condition of Contract. The Contractor shall also provide facilities and services for them as described in the Schedule. The Employer may modify the schedule of other Contractors and shall notify the Contractor of any such modification. |
| ## 9. Personnel | 9.1 The Contractor shall employ either the key personnel named in the Schedule of Key Personnel, as referred to in the SCC, to carry out the functions stated in the Schedule or other personnel approved by the Project Manager. The Employer on the Project Manager’s recommendation will approve any proposed replacement of key personnel only if their qualifications and abilities are substantially equal to or better than those of the personnel listed in the Schedule. |
|  | 9.2 If the Project Manager asks the Contractor to remove a person who is a member of the Contractor’s staff or work force, stating the reasons, the Contractor shall ensure that the person leaves the Site within 7 days and has no further connection with the work in the Contract. |
| ## 10. Skilled/Unskilled Labour | 10.1 Labour based technology shall be applied for construction works at site. The contractor shall employ exclusively national skilled/unskilled labours at construction site. No discrimination for wage payment will be made between men and women and the contractor shall pay equal wage for equal work. 10.2 A child who has not attained the age of fourteen years shall not be employed in any work as a labourer. 10.3 During continuance of the Contract, the Contractor and his sub-contractors shall abide at all times by all labour laws, including child labour related enactments, and rules made there under. |
| ## 11. Risks | 11.1 The Employer carries the risks which this Contract states are Employer’s risks, and the Contractor carries the risks which this Contract states are Contractor’s risks. |
| ## 12. Contractor’s Risks | 12.1 From the Starting Date until the Defects Liability Certificate has been issued, the risks of personal injury, death and loss of or damage to property (including, without limitation, the Works, Plant, Materials and Equipment) are Contractor’s risks. |
| ## 13. Insurance | 13.1 The Contractor shall responsible for necessary insurance coverage from the Start Date to the end of the Defects Liability Period for the following events which are due to the Contractor’s risks: - loss of or damage to the Works, Plant and Materials; - loss of or damage to Equipment; - loss of or damage to property (except the Works, Plant, Materials and Equipment) in connection with the Contract; and - personal injury or death. |

|  | 13.2 Policies and certificates for insurance shall be delivered by the Contractor to the Project Manager for the Project Manager’s approval before the Start Date. All such insurance shall provide for compensation to be payable in the types and proportions of currencies required to rectify the loss or damage incurred. |
| --- | --- |
|  | 13.3 If the Contractor does not provide any of the policies and certificates required, the Employer may effect the insurance which the Contractor should have provided and recover the premiums the Employer has paid from payments otherwise due to the Contractor or, if no payment is due, the payment of the premiums shall be a debt due. |
|  | 13.4 Alterations to the terms of insurance shall not be made without the approval of the Project Manager. |
|  | 13.5 Both parties shall comply with any conditions of the insurance policies. |
| ## 14. Site Investigation Reports | 14.1 The Contractor, in preparing the bid, shall rely on any Site Investigation Reports referred to in the SCC, supplemented by any information available to the Bidder. In accordance with the Instructions to Bidders, Bidders must make their own arrangements to verify the availability and suitability of construction materials when preparing their Bids. |
| ## 15. Queries about the Special Condition of Contract | 15.1 The Project Manager will clarify queries on the Special Condition of Contract. |
| ## 16. Contractor to Construct the Works | 16.1 The Contractor shall construct and install the Works in accordance with the Terms of Reference, Technical Specifications and Drawings. |
| ## 17. The Works to be Completed by the Intended Completion Date | 17.1 The Contractor may commence execution of the Works on the Start Date and shall carry out the Works in accordance with the Program submitted by the Contractor, as per Terms Of References, and complete them by the Intended Completion Date. |
| ## 18. Approval by the Project Manager | 18.1 The Contractor shall submit Specification and Drawings showing the proposed Temporary Works to the Project Manager, who is to approve them if they comply with the Specifications and Drawings. 18.2 The Contractor shall be responsible for design of the Temporary Works. 18.3 The Project Manager’s approval shall not alter the Contractor’s responsibility for design of the Temporary Works. 18.4 The Contractor shall obtain approval of third parties to the design of the Temporary Works, where required. 18.5 All Drawings prepared by the Contractor for the execution of the temporary or permanent Works, are subject to prior approval by the Project Manager before its use. |
| ## 19. Safety | 19.1 The Contractor shall be responsible for the safety of all activities on the Site. |
| ## 20. Discoveries | 20.1 Anything of historical or other interest or of significant value unexpectedly discovered on the Site shall be the property of the Employer. The Contractor shall notify the Project Manager of such discoveries and carry out the Project Manager’s instructions for dealing with them. |
| ## 22. Access to the Site | 22.1 The Contractor shall allow the Project Manager and any person authorised by the Project Manager access to the Site and to any place where work in connection with the Contract is being carried out or is intended to be carried out. |

| ## 23. Instructions | 23.1 The Contractor shall carry out all instructions of the Project Manager, which comply with the laws of Nepal. 23.2 The Contractor shall permit the Donor Agency to inspect the Contractor’s accounts and records relating to the performance of the Contractor and to have them audited by the auditors. |
| --- | --- |
| ## 24. Disputes | 24.1 If the Contractor believes that a decision taken by the Project Manager was either outside the authority given to the Project Manager by the Contract or that the decision was wrongly taken, the decision shall be referred to the Adjudicator within 14 days of the notification of the Project Manager’s decision. |
| ## 25. Procedure for Disputes | 25.1 The Adjudicator shall give a decision in writing within 28 days of receipt of a notification of a dispute. 25.2 The Adjudicator shall be paid by the rate specified in the prevailing rules and/or SCC. 25.3 In case of arbitration, the arbitration shall be conducted in accordance with the arbitration procedures published by the institution named and in the place shown in the SCC. |
| ## 26. Replacement of Adjudicator | 26.1 If the Adjudicator resign or die, or the Employer and the Contractor agree that the Adjudicator is not functioning in accordance with the provisions of the Contract, a new Adjudicator will be jointly appointed by the Employer and the Contractor. within 28 days. |

# B.	Time Control

| ## 27. Program | 27.1 Within the time stated in the SCC, the Contractor shall submit to the Project Manager for approval a Program showing the general methods, arrangements, order, and timing for all the activities in the Works. 27.2 An update of the Program shall be a program showing the actual progress achieved on each activity and the effect of the progress achieved on the timing of the remaining work, including any changes to the sequence of the activities. 27.3 The Contractor shall submit to the Project Manager for approval an updated Program at intervals no longer than the period stated in the SCC. If the Contractor does not submit an updated Program within this period, the Project Manager may withhold the amount stated in the SCC from the next payment certificate and continue to withhold this amount until the next payment after the date on which the overdue Program has been submitted. 27.4 The Project Manager’s approval of the Program shall not alter the Contractor’s obligations. The Contractor may revise the Program and submit it to the Project Manager again at any time. A revised Program shall show the effect of Variations and Compensation Events. |
| --- | --- |
| ## 28. Extension of the Intended Completion Date | 28.1 The Project Manager shall extend the Intended Completion Date if a Compensation Event occurs or a Variation is issued which makes it impossible for Completion to be achieved by the Intended Completion Date without the Contractor taking steps to accelerate the remaining work, which would cause the Contractor to incur additional cost. |

|  | 28.2 The Project Manager shall decide whether and by how much to extend the Intended Completion Date within 21 days of the Contractor asking the Project Manager for a decision upon the effect of a Compensation Event or Variation and submitting full supporting information. If the Contractor has failed to give early warning of a delay or has failed to cooperate in dealing with a delay, the delay by this failure shall not be considered in assessing the new Intended Completion Date. |
| --- | --- |
| ## 29. Acceleration | 29.1 When the Employer wants the Contractor to finish before the Intended Completion Date, the Project Manager will obtain priced proposals for achieving the necessary acceleration from the Contractor. If the Employer accepts these proposals, the Intended Completion Date will be adjusted accordingly and confirmed by both the Employer and the Contractor. |
| ## 30. Delays Ordered by the Project Manager | 30.1 The Project Manager may instruct the Contractor to delay the start or progress of any activity within the Works. |
| ## 31. Management Meetings | 31.1 Either the Project Manager or the Contractor may require the other to attend a management meeting. The business of a management meeting shall be to review the plans for remaining work and to deal with matters raised in accordance with the early warning procedure. 31.2 The Project Manager shall record the business of management meetings and provide copies of the record to those attending the meeting and to the Employer. The responsibility of the parties for actions to be taken shall be decided by the Project Manager either at the management meeting or after the management meeting and stated in writing to all who attended the meeting. |
| ## 32. Early Warning | 32.1 The Contractor shall warn the Project Manager at the earliest opportunity of specific likely future events or circumstances that may adversely affect the quality of the work, or delay the execution of the Works. Extension of time shall only be considered if this warning is timely done by the contractor. 32.2 The Contractor shall cooperate with the Project Manager in making and considering proposals for how the effect of such an event or circumstance can be avoided or reduced by anyone involved in the work and in carrying out any resulting instruction of the Project Manager. |

# C.	Quality Control

| ## 33. Quality Control | 33.1 The Employer shall not appoint the site in-charge at the constructions site for day to day supervision work. This shall be the responsibility of the Contractor. However, the Employer for it's confidence shall make quality control/monitoring by various laboratory test and inspections at the critical construction stages following "Quality Control Manual, Trial Bridge Construction" of Trail Bridge Section/Department of Local Infrastructure and Development of Agricultural Roads/Ministry of Local Development (TBS/DoLIDAR/MoLD).For this the Employer may appoint a qualified consultant or may assign its own engineer. Without test certificates and inspection reports no payment to the Contractor shall be made. In any case, quality control/monitoring by the Employer shall not release the Contractor from its prime responsibility for total quality management and quality assurance. |
| --- | --- |

| ## 34. Quality Assurance | 34.1 Total quality management and quality assurance is the sole responsibility of the Contractor. The quality management and quality assurance shall follow as described in the Terms of Reference and Quality Assurance Document, which are the integral part of the Contract Agreement. The quality assurance must reflect that the executed works/services is in accordance and satisfies the technical specifications and design drawings. Without quality assurance documents no payment to the Contractor shall be made. |
| --- | --- |
| ## 35. Identifying Defects | 35.1 The Project Manager shall check the Contractor’s work and notify the Contractor of any Defects that are found. Such checking shall not affect the Contractor’s responsibilities. The Project Manager may instruct the Contractor to search for a Defect and to uncover and test any work that the Project Manager considers may have a Defect. |
| ## 36. Tests | 36.1 If the Project Manager instructs the Contractor to carry out a test not specified in the Specification to check whether any work has a Defect and the test shows that it does, the Contractor shall pay for the test and any samples. If there is no Defect, the test shall be a Compensation Event. |
| ## 37. Correction of Defects | 37.1 The Project Manager shall give notice to the Contractor of any Defects before the end of the Defects Liability Period, which begins at Completion, and is defined in the Special Condition of Contract. The Defects Liability Period shall be extended for as long as Defects remain to be corrected. 37.2 Every time notice of a Defect is given, the Contractor shall correct the notified Defect within the length of time specified by the Project Manager’s notice. |
| ## 38. Uncorrected Defects after Completion Date | 38.1 If the Contractor has not corrected a Defect within the time specified in the Project Manager’s notice, the Project Manager will assess the cost of having the Defect corrected, and the Contractor will pay this amount. |

# D.	Cost Control

| ## 39. Design, Drawing and Schedule of Works | 39.1 The "Schedule of works" (SOW) shall be read in conjunction with the Design Drawings, Technical Specifications, Instruction the Bidders, Condition of Contract and Terms of Reference. The quantities given in the SOW are estimated and provisional, hence meant only for costing and pricing of the bid by the bidders. The basis of payment will be as per the mode of payment according to the SCC. If any discrepancy arises between SOW and drawing, the quantity as per the drawings shall prevail for calculating the bid price. 39.2 The lump sum price in Construction Turnkey package, except otherwise provided under the contract shall include all construction equipments, tools, plants, labour, materials, transportation, construction, erection, maintenance supervision, insurance, profit, taxes and duties, overhead together with allocation for general risks, liabilities and obligation set out (also unanticipated) in the contract. 39.3 The method of measurement of work for payment shall be in accordance with the "as per completed" work (different construction stages), but not item wise works, which should be according to the drawing. |
| --- | --- |

| ## 40. Variations | 40.1 This Contract is entered into with the understanding that there may always exist a certain degree of difference between the projected works according the approved design, calculated in the cost estimate and actual execution of the work at site. it is also understood that the contract amount specified in the Agreement covers all such differences and/or risks and therefore will not be changed on account of minor differences or eventualities. In any case, no claim shall be entertained regarding porter distance, haulage distance and quantity/classification of excavation works (Soil/Rock etc). 40.2 If due to major changes in design or altered site location, the Contractor should undertake additional or less work than provided for in the contract amount specified in the Agreement, the variation may be made as per rules within the limits described in the following Sub-Clauses. 40.3 On the submission of a proposal for variation in the work either by the Employer or the Contractor, the other party shall depute an authorized representative to verify the proposal and, if necessary, the site conditions and shall make a specific report within 20 days from the date of submission of the proposal about the nature and quantities to be increased or decreased. 40.4 No claims for deduction or addition works within 10% of estimated civil construction cost shall be entertained. 40.5 The clause 40.4 doses not, however pertain to works that has not been designed, such as additional structures. 40.6 No variations whatsoever will be made for cost pertaining to personnel travel, camp running/hiring, overheads, fees etc. |
| --- | --- |
| ## 41. Payment Certificates | 41.1 The Contractor shall submit to the Project Manager statement of the work executed less the cumulative amount certified previously as per SCC. 41.2 The Project Manager shall check the Contractor’s statement (bill) and certify the amount to be paid to the Contractor. 41.3 The value of work executed shall be determined by the Project Manager |
| ## 42. Payments | 42.1 Payments shall be adjusted for deductions of advance payments and retention. The Employer shall pay the Contractor the amounts certified by the Project Manager within 28 days of the date of each certificate as specified in the SCC. 42.2 Subject to clause 40.4 for any additional work made according to a variation order, major structure added, change in composition of designed structure (apart form general arrangement and standard, drawings) shall be paid for based on Employer's cost estimate and its increment/decrement with respect to the contract amount. In case of cancellation of contract with mutual consent between the Employer and the Firm item rate of Cost Estimate shall be deduced from above mentioned basis to calculate the amount of total work done. |
| ## 43. Compensation Events | The following shall be Compensation Events: - The Employer modifies the Schedule of Other Contractors in a way that affects the work of the Contractor under the Contract. - The Project Manager orders a delay or does not issue Drawings, Specifications, or instructions required for execution of the Works on time. - The Project Manager instructs the Contractor to uncover or to carry out additional tests upon work, which is then found to have no Defects. |

|  | - Public authorities, utilities, or the Employer do not work within the dates and other constraints stated in the Contract, and they cause delay. - The advance payment is delayed. - The Project Manager unreasonably delays issuing a Certificate of Completion. - Other Compensation Events described in the Contract or determined by the Project Manager shall apply. |
| --- | --- |
|  | 43.2 If a Compensation Event would cause additional cost or would prevent the work being completed before the Intended Completion Date, the Contract Price shall be increased and/or the Intended Completion Date shall be extended. The Project Manager shall decide whether and by how much the Contract Price shall be increased and whether and by how much the Intended Completion Date shall be extended. |
|  | 43.3 As soon as information demonstrating the effect of each Compensation Event upon the Contractor’s forecast cost has been provided by the Contractor, it shall be assessed by the Project Manager, and the Contract Price shall be adjusted accordingly. If the Contractor’s forecast is deemed unreasonable, the Project Manager shall adjust the Contract Price based on the Project Manager’s own forecast. The Project Manager will assume that the Contractor will react competently and promptly to the event. 43.4 The Contractor shall not be entitled to compensation to the extent that the Employer’s interests are adversely affected by the Contractor’s not having given early warning or not having cooperated with the Project Manager. |
| ## 44. Tax | 44.1 The Project Manager shall adjust the Contract Price if taxes, duties, and other levies are changed between the date 28 days before the submission of Bids for the Contract and the date of the last Certificate of Completion. The adjustment shall be the change in the amount of tax payable by the Contractor, provided such changes are not already reflected in the Contract Price. |
| ## 45. Retention | 45.1 The Employer shall retain from each payment due to the Contractor the proportion stated in the SCC until Completion of the whole of the Works. 45.2 On completion of the whole of the Works and after the Defects Liability Period has passed and the Project Manager has certified that all Defects notified by the Project Manager to the Contractor before the end of this period have been corrected as specified in the SCC. |
| ## 46. Liquidated Damages | 46.1 The Contractor shall pay liquidated damages to the Employer at the rate per day stated in the SCC for each day that the Completion Date is later than the Intended Completion Date. The total amount of liquidated damages shall not exceed the amount defined in the SCC. The Employer may deduct liquidated damages from payments due to the Contractor. Payment of liquidated damages shall not affect the Contractor’s liabilities. 46.2 If the Intended Completion Date is extended after liquidated damages have been paid, the Project Manager shall correct any overpayment of liquidated damages by the Contractor by adjusting the next payment certificate. |
| ## 47. Advance Payment | 47.1 The Employer shall make advance payment to the Contractor of the amounts stated in the SCC by the date stated in the SCC, against provision by the Contractor of an Unconditional Bank Guarantee in a form and by a bank acceptable to the Employer in amounts and currencies equal to the advance payment. The Guarantee shall remain effective until the advance payment has been repaid, but the amount of the Guarantee shall be progressively reduced by the amounts repaid by the Contractor. Interest will not be charged on the advance payment. |

|  | 47.2 The Contractor is to use the advance payment only to pay for Equipment, materials and mobilization expenses required specifically for execution of the Contract. 47.3 The advance payment shall be repaid by deducting the amounts as specified in SCC. |
| --- | --- |
| ## 48. Performance Securities | 48.1 The Performance Security shall be provided to the Employer no later than the date specified in the Letter of Acceptance and shall be issued in an amount and form and by a bank acceptable to the Employer. The Performance Security shall be valid until a date 28 days from the date of issue of the Defects Liability Certificate in the case of a bank guarantee. |
| ## 49. Cost of Repairs | 49.1 Loss or damage to the Works or Materials to be incorporated in the Works between the Start Date and the end of the Defects Liability Period shall be remedied by the Contractor at the Contractor’s cost if the loss or damage arises from the Contractor’s acts or omissions. |

# E.	Finishing the Contract

| ## 50. Completion | 50.1 The Contractor shall request the Project Manager to issue a Certificate of Completion of the Works (Work Completion Certificate), and the Project Manager will do so upon deciding that the work is completed, including all rectification works. |
| --- | --- |
| ## 51. Taking Over | 51.1 The Employer shall take over the Site and the Works within seven days of the Project Manager’s issuing a Certificate of Completion. |
| ## 52. Final Account | 52.1 The Contractor shall supply the Project Manager with a detailed account of the total amount that the Contractor considers payable under the Contract before the end of the Defects Liability Period. The Project Manager shall issue a Defects Liability Certificate and certify any final payment that is due to the Contractor within 56 days of receiving the Contractor’s account if it is correct and complete. If it is not, the Project Manager shall issue within 56 days a schedule that states the scope of the corrections or additions that are necessary. If the Final Account is still unsatisfactory after it has been resubmitted, the Project Manager shall decide on the amount payable to the Contractor and issue a payment certificate. |
| ## 53. Termination | 53.1 The Employer or the Contractor may terminate the Contract if the other party causes a fundamental breach of the Contract. 53.2 Fundamental breaches of Contract shall include, but shall not be limited to, the following: - The Contractor stops work for 28 days when no stoppage of work is shown on the current Program and the stoppage has not been authorised by the Project Manager. - The Project Manager instructs the Contractor to delay the progress of the Works, and the instruction is not withdrawn within 28 days. - The Employer or the Contractor is made bankrupt or goes into liquidation other than for a reconstruction or amalgamation. - A payment certified by the Project Manager is not paid by the Employer to the Contractor within 84 days of the date of the Project Manager’s certificate. - The Project Manager gives Notice that failure to correct a particular Defect is a fundamental breach of Contract and the Contractor fails to correct it within a reasonable period of time determined by the Project Manager. - The Contractor does not maintain a Security, which is required. |

|  | - The Contractor has delayed the completion of the Works by the number of days for which the maximum amount of liquidated damages can be paid, as defined in the SCC. - If the Contractor, in the judgment of the Employer, has engaged in corrupt or fraudulent practices in competing for or in executing the Contract. For the purpose of this paragraph: “corrupt practice” means the offering, giving, receiving or soliciting of any thing of value to influence the action of a public official in the procurement process or in contract execution. “fraudulent practice” means a misrepresentation of facts in order to influence a procurement process or the execution of a contract to the detriment of the Employer, and includes collusive practice among Bidders (prior to or after bid submission) designed to establish Bid Prices at artificial non-competitive levels and to deprive the Employer of the benefits of free and open competition. i. The Contractor does not comply with Clause 10. 53.3 When either party to the Contract gives notice of a breach of Contract to the Project Manager for a cause other than those listed under Sub-Clause 53.2 above, the Project Manager shall decide whether the breach is fundamental or not. 53.4 Notwithstanding the above, the Employer may terminate the Contract for convenience. 53.5 If the Contract is terminated, the Contractor shall stop work immediately, make the Site safe and secure, and leave the Site as soon as reasonably possible. |
| --- | --- |
| ## 54. Payment upon Termination | 54.1 If the Contract is terminated because of a fundamental breach of Contract by the Contractor, the Project Manager shall issue a certificate for the value of the work done and Materials ordered less advance payments received up to the date of the issue of the certificate and less the percentage to apply to the value of the work not completed, as indicated in the SCC. Additional Liquidated Damages shall not apply. If the total amount due to the Employer exceeds any payment due to the Contractor, the difference shall be a debt payable to the Employer. 54.2 If the Contract is terminated for the Employer’s convenience or because of a fundamental breach of Contract by the Employer, the Project Manager shall issue a certificate for the value of the work done, Materials ordered, the reasonable cost of removal of Equipment, repatriation of the Contractor’s personnel employed solely on the Works, and the Contractor’s costs of protecting and securing the Works, and less advance payments received up to the date of the certificate. |
| ## 55. Property | 55.1 All Materials on the Site, Equipment, Temporary Works and Works shall be deemed to be the property of the Employer if the Contract is terminated because of the Contractor’s default. |
| ## 56. Suspension of Donor Agency Loan/Credit/ Grant | 56.1 In the event that the Donor Agency suspends the loan/ credit/grant to the Employer from which part of the payments to the Contractor are being made: - the Employer is obligated to notify the Contractor of such suspension within 7 days of having received the Donor Agency's suspension notice; and - if the Contractor has not received sums due him within the 28 days for payment provided for in Clause 42, the Contractor may immediately issue a 14-day termination notice. |

# F.	Additional Clauses

| ## 57. Project Manger’s Duties and Authority | 57.1 The Project Manager’s duty and authority are restricted to extend of as detailed in the SCC. |
| --- | --- |
| ## 58. Quarries and Spoil Dumps | 58.1 Any quarry operated as part of this Contract shall be maintained and left in a stable condition without steep slopes and be either refilled or drained and be landscaped by appropriate planting. Rock or gravel taken from a river shall be removed over some distance so as to limit the depth of material removed at any one location, not disrupt the river flow or damage or undermine the river banks. The Contractor shall not deposit excavated material on land in Government or private ownership except as directed by the Project Manager in writing or by permission in writing of the authority responsible for such land in Government ownership, or of the owner or responsible representative of the owner of such land in private ownership, and only then in those places and under such conditions as the authority, owner or responsible representative may prescribe. |
| ## 59. Safety, Security and Protection of the Environment | 59.1 The Contractor shall, throughout the execution and completion of the works and the remedying of any defects therein: - Have full regard for the safety of all persons entitled to be upon the site and keep the site (so as the same is under his control) and the works (so far as the same are not completed or occupied by the Employer) in an orderly state appropriate to the avoidance of danger to such persons. - Provide and maintain at his own cost all lights, guards, fencing, warning signs and watching, when necessary or required by the Project Manager or by any duly constituted authority, for the protection pf the Works of for the safety and convenience of the public or others. - Take all reasonable steps to protect the environment on and off the site and to avoid damage or nuisance to persons or to property of the public or others resulting from pollution, noise or other causes arising as a consequence of his methods of operation. - Ensure that any cut or fill slopes are planted in grass or other plant cover as soon as possible to protect them from erosion. This planting shall follow the recommendations given in manuals and handbooks such as “Vegetation structures for stabilizing highway slopes – A manual for Nepal”, department of Roads. - Any spoil or material removed from drains shall be disposed off to designated stable tipping areas as directed by the Project Manager. - Shall not use fuelwood as a means of heating during the processing or preparation of any materials forming part of the works. - The Project Manager shall have the power to disallow any working practice or activity of the Contractor or direct that such practices or activities be modified should the Project Manager consider, on the advice of the relevant Government Departments, that the practices or activities will be harmful to wildlife. - Provide on the Site such life saving apparatus as may be appropriate and an adequate and easily accessible first aid outfit or such outfits as may be required by any government ordinance, factory act, etc., subsequently published and amended from time to time. |
| ## 60. Value Added Tax | 60.1 The Contract is not exempted from value added tax. An amount specified in the schedule of taxes shall be paid by the Contractor in the concerned VAT office. |

| ## 61. Income Taxes on Staff | 61.1 The Contractor’s staff, personal and labour will be liable to pay personal income taxes in Nepal in respect of their salaries and wages, as are chargeable under the laws and regulations for the time being in force, and the Contractor shall perform such duties in regard to such deductions as may be imposed on him by such laws and regulations. 61.2 The issue of the Final Account Certificate pursuant to Clause 52 shall be made only upon submittal by the Contractor of a certificate of income tax clearance from His Majesty’s Government of Nepal. |
| --- | --- |
| ## 62. Duties, Taxes and Royalties | 62.1 Any element of royalty, duty or tax in the price of any goods including fuel oil, lubricating oil, cement, timber, iron and iron goods locally procured by the Contractor for the works shall be included in the Contract rates and prices and no reimbursement or payment in that respect shall be made to the Contractor. 62.2 The Contractor shall familiarise himself with the rules and regulations of Nepal with regard to customs, duties, taxes, clearing of goods and equipment, immigration and the like, and it will be necessary for him to follow the required procedures regardless of the assistance as may be provided by the Employer wherever possible. 62.3 The Contractor shall pay and shall not be entitled to the reimbursement of cost of extracting construction materials such as sand, stone/boulder, gravel, etc. from the river beds or quarries. Such prices will be levied by the local District Development Committee (DDC) as may be in force at the time. The Contractor, sub-contractor(s) employed directly by him and for whom he is responsible, will not be exempt from payment of royalties, taxes or other kinds of surcharges on these construction materials so extracted and paid for to the DDC. |
| ## 63. Member of Government, etc, not Personally Liable | 63.1 No member or officer of HMGN or the Employer or the Project Manager or any of their respective employees shall be in any way personally bound or liable for the act or obligations of the Employer under the Contract or answerable for any default or omission in the observance or performance of any of act, matter or thing which are herein contained. |
| ## 64. Approval of Use of Explosives | 64.1 No explosives of any kind shall be used by the Contractor without the prior consent of the Employer in writing and the Contractor shall provide, store and handle these and all other items of every kind whatsoever required for blasting operations, all at his own expense in a manner approved in writing by the Employer. |
| ## 65. Compliance with Regulations for Explosives | 65.1 The Contractor shall comply with all relevant ordinances, instructions and regulations which the Government, or other person or persons having due authority, may issue from time to time regarding the handling, transportation, storage and use of explosives. |
| ## 66. Permission for Blasting | 66.1 The Contractor shall at all times maintain full liaison with and inform well in advance, and obtain such permission as is required from all Government authorities, public bodies and private parties whatsoever concerned or affected, or likely to be concerned or affected by blasting operation. |
| ## 67. Records of Explosives | 67.1 Before the beginning of the Defects Liability Period, the Contractor shall account to the satisfaction of the Project Manager for all explosives brought on to the Site during the execution of the Contract and the Contractor shall remove all unused explosives from the Site on completion of works when ordered by the Project Manager. |