Section - V

SPECIAL CONDITIONS OF CONTRACT (SCC)

Table of Clauses:

1.	Definitions (GCC Clause 1)	34

2.	Language and Applicable Law (GCC Clause 3)	34

3.	Other Contractor (GCC Clause 8)	34

4.	Personnel (GCC Clause 9)	34

5.	Insurance (GCC Clause 13)	34

6.	Site Investigation reports (GCC Clause 14)	35

7. 	Procedures for  Disputes (GCC Clause 25)	35

8.	Program (GCC Clause 27)	35

9.	Compensation Events (GCC Clause 43)	35

10.	Retention (GCC Clause 45)	35

11.	Liquidated Damages (GCC Clause 46)	35

12.	Payment (GCC Clause 42 and 51)	35

13.	Termination (GCC Clause 53)	37

14.	Payment upon Termination (GCC Clause 54)	38

15.	Project Manager's Duty and Authority (GCC Clause 57)	38

16.	Force Majeure	38

17.	Proprietary Rights of the Employer	38

18.	The Services	38

19.	Release of performance security and retention money	38

20.	Authorized Representative	38

Section - V

Special Conditions of Contract (SCC)

| # 1. Definitions (GCC Clause 1) | 1.1 The Site is located at the following: Bridge No Bridge Name Location .................. .. ......................... .................. ......................... 1.2 The Employer is: District Development Committee's Office,................. 1.3 The Project Manager is: Name: Local Development Officer or his/her authorised representative. Address: District Development Committee's Office,..................................... 1.4 The name and identification number of the Contract is: Long Span Trail Bridges construction under Construction Turnkey Package (CTP) IFB/Contract number.............................................. The Works consist of Long Span Trail Bridges construction under turnkey package. The number of packages that can be offered to any one contractor is limited to Two (2) numbers of bridges in a single running fiscal year. 1.5 The Start Date shall be ..........................................[insert date]. Intended Completion Date shall be ......................[insert date]. 1.6 Defect Liability Period shall be: Six (6) Months from the completion date. |
| --- | --- |
| # 2. Language and Applicable Law (GCC Clause 3) | 2.1 Language of the contract shall be in English. But letter of exchange and communication shall be in Nepali. Law governing the contract is applicable laws of Nepal. |
| # 3. Other Contractor (GCC Clause 8) | 3.1 Other contractors are not allowed. |
| # 4. Personnel (GCC Clause 9) | 4.1 Key personnel as per Schedule of Requirements. |
| # 5. Insurance (GCC Clause 13) | 5.1 The Contractor shall take out and maintain adequate professional liability insurance as well as third party liability. 5.2 The Employer undertakes no responsibility in respect of any life, health, accident, travel and other insurance, which may be necessary or desirable for the personnel and specialists associated with the Contractor for the purpose of the services, nor for any member of family of any such persons. The Contractor shall make insurance for all these risk and liabilities. |

| # 6. Site Investigation reports (GCC Clause 14) | 6.1 Site Investigation Reports shall be given by the Employer, if any. |
| --- | --- |
| # 7. Procedures for Disputes (GCC Clause 25) | 7.1 The dispute resolution mechanism to be applied pursuant to GCC shall be referred to adjudication/arbitration in accordance with the Arbitration Act, 1981; and prevailing Laws. |
| # 8. Program (GCC Clause 27) | - 8.1 Within 7 days of site possession date or Work order date whichever is earlier. |
| # 9. Compensation Events (GCC Clause 43) | - 9.1 Works starting date shall be deemed as Site Possession Date. This provision shall be prevailed for extension of time only. |
| # 10. Retention (GCC Clause 45) | 10.1 Retention money for each payment shall be 5%. |
| # 11. Liquidated Damages (GCC Clause 46) | 11.1 Liquidated Damages rate applied for is 0.05% per day and total amount of Liquidated Damages shall not exceed 10% of the contract price |
| # 12. Payment (GCC Clause 42 and 51) | 12.1 Payment for the Works shall be made in Nepali Rupees, as follows: - The Employer shall pay to the Contractor as a mobilization, an amount not exceeding to 15% of the total contract amount for the package against a provision of a bank guarantee valid for a period to cover till such advance is recovered (at least 6 months), upon such demand made by the Contractor and within a fortnight. - An amount up to 40% of the total contract amount for the package shall be paid (15% of the mobilization advance will be deducted) within 30 days after submission of the Inspection Certificate from Employer’s Engineer and Quality Assurance Documents from the Contractor stating that the steel parts are fabricated according to the Employer’s requirement and the standard specification. Inspection Certificate shall be issued by the Employer's Engineer. The payment will be made either after all the fabricated steel parts are transported to the site or a Bank Guarantee equivalent to 25% of the total contract amount is produced after fabrication work is completed in the workshop. - An amount up to 20% of the total contract amount for the package shall be paid within 30 days after receipt of the Progress Report with Quality Assurance (QA) documentation from the Contractor and Civil Work Inspection Form issued by Employer's Engineer certifying that the camp installation, layout and excavation of all foundations have been completed. The QA documentation shall contain chronological photographs illustrating complete foundations of all anchorage blocks with staff and measuring tape (graduation on staff/measuring tape shall be easily readable on photographs) confirming the dimensions of the foundation pit (length, breadth, front and back height). |

|  | - An amount up to 20% of the total contract amount shall be paid within 28 days after receipt of the Work Completion Report with Quality Assurance (QA) documentation from the Contractor and remaining 20% of the contract amount shall be paid within 28 days of Work Completion Certificate issued by the Employer's Engineer after final checking of the completed bridge provided the works are acceptable in all aspect. The QA documentation shall contain Album with chronological photographs and Work Records as prescribed in the Quality Control Scheme. The Album shall comprise the systematic photographs of all the construction activities from excavation up to the completion of the bridge confirming the layout of the bridge, quality of material used, dimensions of every structural element at each construction stage, details of the completed bridge components. Final Acceptance of funding agency may necessary, if it is applicable. |
| --- | --- |
|  | - In addition to conditions stipulated in above, the performance security and retention money shall be released only after maintenance period of 6 months upon issue of the final inspection report by the Employer's appointed authorized Engineer, if the bridge is still acceptable and withstand the maintenance period. Important Note : i) Whatever has been written above in 12.1 (a) and (b), the total payment made up to (b) shall not exceed the estimated cost for the fabrication of steel parts. ii) If the amount paid up to (b) is less than the percentage mentioned in respective schedules, the remaining amount shall be adjusted in the forthcoming payment schedules proportionately, i.e. the remaining shall be added to the balance and the percentage taken from that total amount. iii) In case of a bridge site situated in a too remote area and if the transportation cost component is significant (porter distance more than 4 days), the percentage of payments in the above schedule shall be adjusted during agreement in such a way so as not to make too much surplus payment than the actual work conducted. 12.2 Performance Security shall be issued equivalent to 5% of contract price in the form as prescribed in the Sample Forms and shall cover the period of 12 month. 12.3 Payments shall be made against the handing over by the Contractor of the following documents: 12.3.1 Contractor shall submit bill in the standard format as agreed by the Employer. The Contractor shall pay or reimburse to the Employer in respect of the Services, but subject to the contract amount as specified in the Contract Agreement and the provision stipulated under (ii) and (iii) below, for all items of work as stipulated in the Bid Document and according to the conditions mentioned hereunder. 12.3.2 All taxes, duties and levies (except VAT) applicable in the course of this contract shall be borne by the Contractor as per prevailing rules and regulations of HMG/ |

| # 13. Termination (GCC Clause 53) | 13.1 Stalling, Resuming and Suspending the Contract Under following conditions, the Employer may by written notice to the Contractor stall, resume or suspend in whole or in part any or all of the payments/contract: a) If a situation arises because of technical reasons, that the works cannot be carried out without verifying, rectifying, or even redesigning; in such case the contract can be stalled temporarily by issuing a letter and can be resumed again by issuance of another letter from the Employer. However, the time lapse between those two letters shall not exceed three months. b) A default shall have occurred in the execution of the terms under the contract on the part of the Contractor. c) Any other condition, which has arisen which, in the reasonable opinion of the Employer, interferes, or threatens to interfere with the successful carrying out of the project or the accomplishment of the purposes of the contract. 13.2 Termination of the Contract by the Employer The Employer, may by written notice to the Contractor, terminate the Contract under any of the following events: a) If the work can not be continued after three months after it has been stalled as mentioned in clause 13.1 (a), because of serious technical problem. b) Any of the conditions referred to in clause 13.1 (b) and (c) shall continue for a period of fifteen (15) days after the Employer shall have given written notice to the Contractor of suspension of payments to Contractor under the Contract. c) In any event, the Employer may terminate the Contract at any time by giving not less than thirty (30) days’ prior written notice to the Contractor. 13.3 Termination of the Contract by the Contractor The Contractor shall notify the Employer in writing of any situation or of the occurrence of any event beyond the reasonable control of the Contractor, which makes it impossible for the Contractor to carry out his obligations. Upon confirmation in writing by the Employer of the existence of any such situation or event, or upon failure of the Employer to respond to such notice within forty five (45) days of receipt thereof, the Contractor shall be relieved from all liability from the date of such receipt for failure to carry out such obligations, and the Contractor may thereupon terminate the Contract by giving not less than thirty (30) days’ prior written notice thereof. |
| --- | --- |
|  | 13.4 Termination Procedure a) Upon termination of the Contract under Section 13.2 (a, b, c) or 13.3, the Contractor shall take immediate steps to terminate the services in a prompt and orderly manner and to reduce loses and to keep further expenditure to a minimum. b) Upon termination of the Contract (unless such termination shall have been occasioned by the default of the Contractor), the Contractor shall be entitled to be reimbursed in full for such cost as shall have been duly incurred prior to the date of such termination and for reasonable costs incident to the orderly termination of the services, but shall be entitled to receive no other or further payments. |

| # 14. Payment upon Termination (GCC Clause 54) | The whole amount shall be suspended until the works could be completed by another contractor or force account. |
| --- | --- |
| # 15. Project Manager's Duty and Authority (GCC Clause 57) | As per Prevailing Laws, Schedule of Requirement, Technical Specification and other manual issued by the relevant authority. |
| # 16. Force Majeure | 16.1 If either party is temporarily unable by reason of force majeure to meet any of its obligations under the Contract, and if such party gives to the other party written notice of the event within fifteen (15) days after its occurrence, such obligations of the party as it is unable to perform by reason of the event shall be suspended for as long as the inability continues. 16.2 Neither party shall be liable to the other party for loss or damage sustained by such other party arising from any event referred for this contract, delays arising from such event. 16.3 The term ‘Force Majeure’ as employed herein shall mean acts of public enemy, strikes, wars, blockades, insurrection, riots, epidemic, landslides, earthquake, storms, lightening, civil disturbances, explosions, and other similar events not within the control of either party and which by the exercise of due diligence neither party is able to overcome. |
| # 17. Proprietary Rights of the Employer | 17.1 All reports and relevant data such as maps, diagrams, plans, statistics and supporting records or materials compiled or prepared in the course of the services shall be confidential and shall be absolute property of the Employer. The Contractor agrees to deliver all these materials to the Employer upon completion of this contract. The Contractor may retain a copy of such data but shall not use the same for purpose unrelated to this contract without prior written approval of the Employer. |
| # 18. The Services | 18.1 The services for the packages described in Instruction to Bidder under this Contract in accordance with the Terms of Reference, Technical Specifications, and Quality Assurance Document set forth herein shall be performed professionally and accurately by the Contractor. 18.2 The Employer shall make available free of any charge, the service, facilities described in Terms of Reference. |
| # 19. Release of performance security and retention money | 19.1 Performance bond (guarantee) will be released only after completion/expiry of maintenance period of 6 months within which the Employer shall make a final check regarding the concerned bridge/s. Retention money will be refunded upon receipt of income tax clearance certificate and the acceptance of the bridge by the donor’s representative in case of donor funded bridge. 19.2 If the contractor does not make rectification as suggested during final check/s within the 6 month’s maintenance period then the rectification shall be made by the Employer's Engineer by a suitable means and the extra cost incurred for such work shall be deducted from the contractor’s account, retention money and or will be recovered from the bank (performance) guarantee. |
| # 20. Authorized Representative | 20.1 Any action required or permitted to be taken, and any document required or permitted to be executed, under this contract, may be taken or executed on behalf of the Contractor by the Executive Director or his designated representative and on behalf of the Employer by the Chief of DDC Office or his designated representative. Such designation of authority shall be duly performed in writing and supported by any other required documents, whatsoever. |