Section - VI

SCHEDULE  OF  REQUIREMENTS (SOR)

Table of Clauses:

Schedule A	40

Completion Date	40

1.	Notice of Delay	40

2.	Time Extension	40

3.	Penalties for Delay	40

Schedule B	40

Time/Work Schedule	40

Manning Schedule (sample)	41

Schedule C	41

Qualification Requirement	41

1.	Contractor	41

1.1	Contractor's Experience and Performance	41

1.2	Personnel	42

1.3	Construction Equipments	42

1.4	Financial Status	43

2.	Fabricator	43

2.1	Fabricator's Experience and Performance	43

2.2	Personnel	43

2.3	Tools and Equipments	44

3.	Others	44

Section - VI

Schedule of Requirements (SOR)

# Schedule A

## Completion Date

The completion date of the Works as within 8 (Eight) months stipulates hereafter a Intended completion date which is the date of completion at ........................[insert date] of the construction works of..........................................................[insert the name of the bridge] and handover to the ....................................................[name of the authority to handover] in the site as turnkey basis.

Long Span Trial Bridges construction under Construction Turnkey Package is effective from the date of getting Work Order for this works.

The Quantity of the Works required is as per Design Drawings (Prevailing) and Schedule of Works (Reference).

Other requirements and conditions are as follows:

### 1.	Notice of Delay

In the event that the Contractor encounters a delay in obtaining the required services and facilities set forth for the provision of service/works, the Contractor shall promptly notify the Employer of such delay with documentary evidence and may request for time extension for completion of the project before expiry of the stipulated time.

### 2.	Time Extension

Time extension will be granted according to prevailing Local Self Governance Financial Administration Regulation and shall apply only if the reasons are acceptable to the Employer.

### 3.	Penalties for Delay

In case of reported delays in the performance of the service/works beyond the specified time of completion due to Contractor’s default, the penalty will be determined as per the conditions of contract.

# Schedule B

## Time/Work Schedule

Propose a compatible and realistic time schedule (time required for activities) based on the said work nature. While preparing the time schedule, all the activities, their requirement of time and resource personnel with their inputs has to be incorporated based on detailed Terms of Reference (ToR).

A realistic manning schedule (input of personnel), and time schedule (time required for activities), based on the field situation of the said work and proposed as compatible to the whole bid shall be made and submitted. While preparing the time schedule and manning schedule, all the activities, their requirement of time and resource personnel with their inputs has to be incorporated based on detailed Terms of Reference (ToR).

Time/ Work schedule (sample)

| Description of Work | Year …….... |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 |
| Fabrication |  |  |  |  |  |  |  |  |  |  |  |
| Layout/foundation excavation |  |  |  |  |  |  |  |  |  |  |  |
| Masonry/concrete work |  |  |  |  |  |  |  |  |  |  |  |
| Tower erection |  |  |  |  |  |  |  |  |  |  |  |
| Cable hoisting |  |  |  |  |  |  |  |  |  |  |  |
| Bridge erection |  |  |  |  |  |  |  |  |  |  |  |

## Manning Schedule (sample)

| Designation | Year………. |  |  |  |  |  | Year……….. |  |  |  |  |  | Field Man- | Office Man- | Total Man- |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | 1 | 2 | 3 | 4 | 5 | 6 | 1 | 2 | 3 | 4 | 5 | 6 | Month | Month | month |
| Team Leader/ Coordinator |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Site Overseer |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Bridge Mechanics |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

- Attach separate paper when required

# Schedule C

## Qualification Requirement

### 1.	Contractor

#### 1.1	Contractor's Experience and Performance

| Description of Works | Minimum required Nos. of Successfully completed Works |
| --- | --- |
| Fabrication and Construction of LSTB Bridges (or former SBD type Bridge) under turnkey Construction Package | 2 Bridges |

1.1.1	A Contractor should have minimum experience of Two number of successfully completed Fabrication and Construction of LSTB Bridges (or former SBD type Bridge) under Construction Turnkey Package within last five years.

#### 1.2	Personnel

| Designation | Minimum Required Nos. of Persons |
| --- | --- |
| Team Leader (Coordinator) | 1 |
| Construction Supervisor (Minimum Overseer Level) | 1 |
| Bridge Fitter (Mechanics) | 2 |

1.2.1	All of these personnel should have minimum 3 years of experience in related field i.e. Construction and Construction Supervision works in general and minimum of two successfully completed LSTB (or former SBD type Bridge).

1.2.2	The Services/Works shall be carried out by the leading Contractor in conjunction with the personnel specified by the Contractor in Manning Schedule (hereinafter called the Personnel) at the time of bidding with the Contractor singularly being responsible for any works carried out by its personnel and partners.

1.2.3	Except as the Employer may otherwise agree, no changes shall be made in the Personnel.  If for any reason beyond the reasonable control of the Contractor it becomes necessary to replace any of the Personnel, the Contractor shall provide as replacement, a personnel of equivalent qualifications with prior written approval of the Employer.

1.2.4	In the event that any personnel specified in the manning schedule is found to be inadequately qualified or incompetent in discharging his assigned duties, the Employer may request the Contractor to provide as a replacement, a personnel with qualifications and experience acceptable to the Employer.

1.2.5	In respect of any personnel provided as a replacement, all additional costs arising out of or incidental to such replacement shall be borne by the Contractor.

1.2.6	Team Leader:

The Contractor shall ensure that all the times during the entire phase of the work a team leader acceptable to the Employer shall take charge of the operation of the personnel. The team leader shall be responsible for liaison on the field and or office between the Contractor and the Employer.

1.2.7	Skilled/Unskilled Labors:

Labour based technology shall be applied for construction, maintenance work at site. The Contractor shall employ exclusively local skilled/unskilled labours at the construction site. No discrimination for wage payment will be made on the basis of gender, castes or ethnicity.  The Contractor shall pay equal wage for equal work.  The above will be strictly monitored by the Employer during the site inspection.

#### 1.3	Construction Equipments

| Description | Minimum required number |
| --- | --- |
| Grip Hoist Machine | 3 |
| Rock Drill Machine | 1 |
| Survey Equipment (Minimum Theodolite or Level Machine) | 1 |

It is mandatory to make physical verification by the evaluation team to confirm the actual availability of above manpower and equipments with the Contractor prior to evaluation.

#### 1.4	Financial Status

| Financial Capability | Minimum required |
| --- | --- |
| Bonding Capacity | 5 Lakh |
| Net Worth | 20 Lakh |
| Liquid Assets | 8 Lakh |

The Contractor shall have to present latest Audited Financial Statements and other relevant documents certified by the bank to prove bonding capacity.

### 2.	Fabricator

The proposed fabricator should fulfil following requirements:

#### 2.1	Fabricator's Experience and Performance

| Description of Works | Minimum required Nos. of Successfully completed Works |
| --- | --- |
| Fabrication of steel parts of LSTB Bridges (or former SBD type Bridge) | 5 Bridges |

A Fabricator should have minimum experience of five number of successfully completed fabrication of steel parts of LSTB (or former SBD type Bridge).

#### 2.2	Personnel

| Designation | Minimum Required Nos. of Persons |
| --- | --- |
| Workshop Engineer | 1 |
| Foreman/Overseer/Mechanics (any of one) | 2 |
| Trained welder | 4 |
| Skilled Labours | 10 |

2.2.1	All of these personnel should have minimum 3 years of experience in related field i.e. Fabrication of steel parts of LSTB Bridges (or former SBD type Bridge), and minimum 5 nos. of successfully completed LSTB bridges.

2.2.2	The Services shall be carried out by the leading Contractor in conjunction with the personnel specified by the Contractor in Manning Schedule (hereinafter called the Personnel) at the time of bidding with the Contractor singularly being responsible for any works carried out by its personnel and partners.

2.2.3	Except as the Employer may otherwise agree, no changes shall be made in the Personnel.  If for any reason beyond the reasonable control of the Contractor it becomes necessary to replace any of the Personnel, the Contractor shall provide as replacement, a personnel of equivalent qualifications with prior written approval of the Employer.

2.2.4	In the event that any personnel specified in the manning schedule is found to be inadequately qualified or incompetent in discharging his assigned duties, the Employer may request the Contractor to provide as a replacement, a personnel with qualifications and experience acceptable to the Employer.

2.2.5	In respect of any personnel provided as a replacement, all additional costs arising out of or incidental to such replacement shall be borne by the Contractor.

2.2.6	Skilled/Unskilled Labors:

Labour based technology shall be applied for construction, maintenance work at site. The Contractor shall employ exclusively local skilled/unskilled labours at the construction site. No discrimination for wage payment will be made on the basis of gender, castes or ethnicity.  The Contractor shall pay equal wage for equal work.  The above will be strictly monitored by the Employer during the site inspection.

#### 2.3	Tools and Equipments

| Require Tools and Equipments | Minimum required number of tools and machines |
| --- | --- |
| Saws | 3 |
| Drilling Machine | 3 |
| Welding Machines with voltage stabilizers | 3 |
| Grinder | 3 |
| Lathe machines | 1 |
| Gas cutting equipment | 2 |
| Blacksmith shop | 1 |
| Galvanizing Plant with complete set up (refer to Section VII, clause 351 for schedule of requirements) Installed Temperature Meter Hydrometer PH - Meter Adhesion Testing Hammer Zinc Coat Measuring Instrument Weighting Machine | Own or Sub-letting 1 3 2 1 1 1 |

2.3.1	It is mandatory to make physical verification by the evaluation team to confirm the actual availability of above manpower and equipments with the fabricator prior to evaluation.

### 3.	Others

Apart from as described above, the firm must submit all documents given as Enclosures in the Technical proposal form.

Fabrication of steel parts and site works is to be executed simultaneously.